FORM D: REVISION OF A CAPITAL APPLICATION

| PROJECT NAME: | e-Requisitioning |  |  |
| --- | --- | --- | --- |
| PROJECT LEADER: | Mike Jacklin | CA NO: |  |
| DATE: | 4 March 2024 |  |  |

| A | PROJECT DESCRIPTION |
| --- | --- |
| January 2023 SAGE has been implemeted as the standardized Financial ERP System. The software implemented is reliant on paper based transactions and manual capturing: Paper based Stock and Purchase Requisitions which results in operational risk: - Originators are not electronically requisitioning from the SAGE Stock Catalogue - Supply Chain are having to manually look up and marry Originator Requisitions to actual stock - Supply Chain have to physically capture the Stock and Purchase Requisitions into SAGE - Inventory alogorithm management is not possible due to the unreliability of goods purchased as non stock when they should be stock - Finance is unable to effectively manage budgets before the purchase commitment is made - Request for Quotes are all undertaken manually by e-mail and not through SAGE. - Electronic DoA authorisation is not possible - Management operational reports for Expeditiong, PO management, Performance management is all paper based and suject to error. Stock receipt is problematic due to only local RF currency PO’s being placed in SAGE. |  |

| B | REASON FOR THE REVISION |
| --- | --- |
| March 2023 Revision Original 4Flow Quotation for the Trinity Originator to electronically requisition Stock and Non-Stock did not include for the Requisition Originator to electronically load Stock and Non Stock Requisitions directly into SAGE. Now included. In addition, we require the scope to include On Site training and 4Sight has updated their offer to include: a. User Acceptance Testing: To be undertaken at Rutongo. Attended by User Champions: Finance Benon, IT Olivier, Procurement Rogers, Stores & Inventory Alexis, Mining, Engineering. b. On Site Training and Go Live: To be undertaken at each Mine site. Attended by all disciplines who will use the system including the above champions. September 2023 Revision Supply Chain, Finance and IT undertook at Trinity (Rutongo) 16/17 August a Design Workshop with two representatives from 4Flow: The workshop identified the following Out of Scope Processess: - 4 Flow costs (airline, accommodation and food) has not been included for 4 Flow to attend at Trinity, Design Workshops, User Acceptance Testing to be undertaken at Rutongo and User Training to be undertaken at the 3 Mine Sites. - The Design Worshop also identified system processes not included in theoriginal scope and Capital Application - Intercompany Purchases - Borrowing explosives and intercompany adjustments - Emergency/Breakdown process - Customized Trinity Specific Training/User - Software for Intercompany and Borrowing March 2024 - Approximately 75 Trinity Originators and Approvers participated in the February 2024 Go Live User Acceptance Testing and User Training. Our scope included for 50 licenses. 4Flow make licenses available in quantities of 50. Additional 50 licenses requested $ 3 336.00 - Go Live was planned to be 7:00 4 March 2024 As a result of Trinity February participation in testing and training, the design team has had to make setup changes to the design over the weekend 2/3 March. These changes delayed our Go-Live to 17:00 4th Mar in order to ensure optimum system setup and minimize any post Go-Live issues. As a consequence, the Planned Hand Holding at Rutongo has been moved to Thursday 7 March. This change has impacted on the return date of the 2 4Flow Project implementers from Thursday 7 March to Friday 8 March. $ 1 360.00 |  |

| C | COSTS |  |
| --- | --- | --- |
| Approved Costs |  | $ 41 024 |
| Revised Costs |  | $ 45 720 |
| VARIANCE - Additional 50 Licenses $ 3 336.00 - Extension by 1 day of 4 Flow On Site Project Implementors $ 1 360.00 |  | $ 4 696 |

| D | RISK ASSESSMENT/PREVENTIVE MEASURES INTRODUCED |
| --- | --- |

| E | COMMENTS |  |
| --- | --- | --- |
| CFO |  |  |
| BOARD |  |  |

| D | APPROVAL |  |
| --- | --- | --- |
| CFO |  |  |
| Board |  |  |

NOTE: attach additional quotes or supporting documents if necessary

Included in the covering e-mail 4 March 2024