FORM B: CAPITAL APPLICATION

| PROJECT NAME: | NYAKABINGO DIAMOND DRILLING |  |  |
| --- | --- | --- | --- |
| PROJECT LEADER: | JUSTIN UWIRINGIYIMANA | CONS. ASS. NO.: |  |
| DATE: | 13 AUGUST 2024 | CA NO.: |  |

| A | PROJECT DESCRIPTION |
| --- | --- |
| Hole ID; Easting; Northing; RL; Target Depth; Azimuth; Inclination. NYDD_01; 831114.60; 9794140.50; 2000.00; 700.00; 230.00; -70.00. NYDD_02; 830979.70; 9794335.30; 2006.00; 700.00; 230.00; -70.00. Nyakabingo diamond drilling will test the depth extent of mineralized veins and the host graphitic shales. Two diamond drill holes are planned with a total of 1400 metres. Each hole will extend to 700 metres inclined at 70 degrees to reach an extra 10 levels below BV22. The purpose is to understand the orebody and gain more information to support the ongoing resources estimates as well as add confidence in the ongoing and/or planned infrastructure such as the BV22 Decline, process plant and tailing facilities. |

| B | MOTIVATION |
| --- | --- |
| The purpose is to understand the orebody and gain more information to support the ongoing resources estimates as well as add confidence in the ongoing and/or planned infrastructure such as the BV22 Decline, process plant and tailing facilities. |  |

| C | COSTING SELECTED OPTION |  |
| --- | --- | --- |
| Details can be found in annex A accompanying this form |  |  |
| TOTAL COSTS INCLUDING CONTINGENCIES |  | USD391,835 |
| BUDGET IN 5-YEAR PLAN |  | N/A |
| VARIANCE |  |  |

| D | RISK ASSESSMENT |
| --- | --- |
| - Weather with heavy rains may slow the project in October and November and increase the operational and non-operational charges. - Some budgeted items can only be estimated and there may be some variance. A 20% contingency is included in the budget. - The project may last longer than the two months planned. This will depend on a number of factors including weather, ground conditions, equipment life and performance. - Lab performance may be poor and require re-analysis but it could be done free of charge. - The project may have to be terminated or be called earlier due to poor ground and target failure. The holes may be extended deeper if the rig performance and ground conditions allow. |  |

| E | PROJECT SCHEDULE |
| --- | --- |
| - Equipment, tools and consumables sourcing: Early September-Late September 2024 - Drilling, logging, sampling: Mid-September – Late October 2024 - Results reception, interpretation and reporting: Early December 2024 – Early February 2025. |  |

| F | COMMENTS |  |
| --- | --- | --- |
| GROUP FINANCE |  |  |
| CEO |  |  |
| DIRECTOR |  |  |

| G | APPROVAL |  |
| --- | --- | --- |
| CEO |  |  |
| BOARD |  |  |

NOTE: attach additional quotes or supporting documents if necessary