| DELIVERABLES (DFC TA Grant) | KEY TASKS | Timeline | COSTS (US $) | Rutongo | Nyakabingo | Musha |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 60% | 15% | 25% |
| 1. Detailed SOW, R&R and Programme for the TM&RR project | 1.1 Development of a Scope of Works (incl. workshops and meetings) | Jan 2025 (MP 2) | $ 20 100 | $ 12060 | $ 3015 | $ 5025 |
|  | 1.2. Input into the Stakeholder Engagement Plan (SEP) to inform river rehabilitation and management strategies. |  | $16 650 | $ 9990 | $ 2497,50 | $ 4162,50 |
| 1.2. Mapping of all sources and receptors of contamination and GIS Analysis | 1.2.1. Desktop mapping and Geographic Information System data derivation. | April 2025 (MP 3) | $ 24 950 | $ 14970 | $ 3742,50 | $ 6237,50 |
|  | 1.2.2. Source, pathway and receptor analysis, including a review of gaps in ESIA assessments. |  | $ 23 900 | $ 14340 | $ 3585 | $ 5975 |
|  | 1.2.3. Hydrocensus – location of community water sources (springs) and nature of utilisation. |  | $ 10 550 | $ 6330 | $ 1582,50 | $ 2637,50 |
| 1.3. Determination of the PES of all the river systems | 1.3.1. Ecological health and drivers of the river and wetland ecosystems. | April 2025 (MP 3) | $ 49 700 | $ 29820 | $ 7455 | $ 12425 |
| 1.4. Ecosystem Goods and Services Assessment | 1.4.1. Ecosystem Goods and Services Assessments. | Sept 2025 (MP 4) | $ 36 900 | $ 22140 | $ 5535 | $ 9225 |
| 1.5. Catchment hydrological models | 1.5.1. Modelling catchment hydrological flows and sediment movements. | Sept 2025 (MP 4) | $ 65 450 | $ 39270 | $ 9817,50 | $ 16362,50 |
| 1.6. Flood line Determination Report | 1.6.1 Determining flood lines for major streams, including climate change scenarios. | Sept 2025 (MP 4) | $ 47 200 | $ 28320 | $ 7080 | $ 11800 |
| Sub-Total |  |  | $ 295 400 | $ 177240 | $ 44310 | $ 73850 |

| OTHER TASKS (Trinity Cost-Share) |  |  |  | Rutongo | Nyakabingo | Musha |
| --- | --- | --- | --- | --- | --- | --- |
| DELIVERABLES | KEY TASKS | Timeline | COSTS (US $) | 60% | 15% | 25% |
| 1.7. Water quality monitoring database and dashboard, incorporating existing and future data | 1.7.1 Reviewing water quality monitoring protocols including the development of an online water quality monitoring database and dashboard. | April 2025 (MP 3) | $ 18 650 | $ 11190 | $ 2797,50 | $ 4662,50 |
| Sub-Total |  |  | $ 18 650 | $ 11190 | $ 2797,50 | $ 4662,50 |
| TOTAL |  |  | $ 314 050 | $ 188430 | $ 47107,50 | $ 78512,50 |