## Slide 1: Backup & Disaster Recovery (BDR) Project (Cloud-Based)
Ensuring Business Continuity & Data Protection Managed By: Olivier NEMEYE | Group ICT Manager Supervised By: Rene RUGANJI | Group Network Security & Systems Lead
Period: January – December 2025

## Slide 2: Agenda
1 | Project Overview & Objectives
2 | Project Phases & Timeline
3 | Technical Specifications & Infrastructure
4 | Risk Management & Success Factors
5 | Next Steps & Call to Action

## Slide 3: Project Overview & Objectives
Category | Details
Project Name | Backup & Disaster Recovery (BDR) Implementation – Cloud-Based
Project Manager | Nemeye Olivier
Supervisor | Rene Ruganji – Group Network Security & Systems Lead
Objective | Implement a cloud-based backup & disaster recovery solution to ensure business continuity, data security, and rapid recovery in case of system failure.
Key Goals | ✅ Secure cloud backup for Sage ERP, 4Flow, and Synology Shared Drive ✅ Automated failover & rapid recovery ✅ Compliance with ISO 27001, GDPR ✅ Scalable for future system expansions
Critical Systems | - Sage ERP (Finance & Operations) - 4Flow (Supply Chain Management) - Synology DS220+ Shared Drive (File Storage) - Future Enterprise Systems
Project Duration | January – December 2025

## Slide 4: Project Phases & Timeline
Phase | Key Activities & Deliverables | Timeline
Phase 1: Planning & Requirements | - Define business continuity objectives - Identify critical systems (Sage, 4Flow, Synology) - Assess current IT infrastructure & storage needs - Define budget & technical specifications | Jan – Feb 2025
Phase 2: Vendor Selection & Procurement | - Issue Request for Proposal (RFP) - Evaluate vendor proposals based on security, scalability, support, and cost - Shortlist vendors (Microsoft Azure, AWS, Veeam, Acronis) - Conduct proof-of-concept (PoC) testing - Finalize contracts & procure licenses and hardware | Mar – Apr 2025
Phase 3: System Design & Setup | - Establish cloud-based backup architecture (Hybrid: Cloud + On-Premise) - Configure network security & VPN - Implement AES-256 encryption & MFA policies - Set up on-premise backup appliance (e.g., Synology RS1221+, Dell PowerProtect) - Conduct preliminary backup & restore tests | May – Jun 2025

## Slide 5: Project Phases & Timeline
Phase | Key Activities & Deliverables | Timeline
Phase 4: Implementation & Testing | - Deploy full backup system - Perform failover testing & disaster recovery drills - Simulate cyberattack scenarios to assess security - Establish monitoring tools for backup success tracking - Optimize storage & retention policies | Jul – Sep 2025
Phase 5: Training & Optimization | - Train IT staff on backup management & security - Develop Standard Operating Procedures (SOPs) - Conduct regular audits & compliance checks | Oct – Nov 2025
Phase 6: Full Deployment & Monitoring | - Complete transition to cloud-based backup - Implement continuous monitoring & reporting - Schedule quarterly disaster recovery drills - Document best practices for future scalability | Dec 2025

## Slide 6: Technical Specifications & Preferred Solutions
Requirement | Preferred Solution
Cloud Providers | Microsoft Azure Backup, AWS Backup, Google Cloud, Veeam Cloud Connect, Acronis Cyber Protect
Storage Capacity | Minimum 10TB, expandable storage
Backup Types | Incremental, Differential, Full System Image Backup
Backup Frequency | Critical Systems (Sage, 4Flow) → Every 15 min Shared Drives → Daily snapshots
Security Features | AES-256 Encryption, Multi-Factor Authentication (MFA), Immutable Backups
Compliance Standards | ISO 27001, GDPR, NIST, SOC 2
Disaster Recovery Time | Failover in <1-hour, Geo-Redundant Storage
Monitoring & Alerts | Real-Time Reporting, Email & SMS Alerts
A. Cloud Backup & Disaster Recovery Solution

## Slide 7: Technical Specifications & Preferred Solutions
Component | Preferred Model & Features
On-Premise Backup Appliance | Synology RS1221+, Dell PowerProtect DD3300, HPE StoreOnce 3640
RAID Configuration | RAID 10 or RAID 6 (for redundancy & performance)
Network Support | 10GbE Ethernet Support
Cloud Storage | Amazon S3, Azure Blob, Google Cloud Storage
Replication | Multi-Region Data Redundancy
B. Storage Infrastructure (On-Premise & Cloud)

## Slide 8: Risk Management & Success Factors
Risk | Mitigation Strategy
Cloud Downtime | Multi-region redundancy to ensure availability
Cybersecurity Threats | Regular penetration testing, endpoint protection
Data Loss | Immutable, encrypted backups for recovery
Budget Constraints | Cost-optimized vendor selection