## Dusty Progress Report
Trinity Metals Drafts Standard Operating Procedures (Progressive Report)
No. | Standard Operating Procedure | 1 st Draft Date (Dusty to Tertia) | 2nd Draft Date (Return Draft from Tertia) | 3nd Draft Date | Online Review |  | Final Draft Date | Comments | % Complete | Completed Y/N | Review Date | Rutongo Review Team | Musha Review Team | Nyakabingo Review Team
TM 01 SOP | Barring Procedure | 2024-01-17 | 2024-08-08 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18 | Johan Fourie (Mine Superintendent) | Mike Chiguware (Mine Superintendent) | Wisdom Mugwagwa (Group Chief Surveyor)
TM 02 SOP | Use Of Rockdrill Machine | 2024-01-04 | 2024-08-08 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18 | Kevin Kayiranga (OHS Superintendent) | Benita Twabaze(SHEC Superintendent) | Imanirafosha Esperance (SHEC Superintendent)
TM 03 SOP | Loco Operation | 2024-01-17 | 2024-08-08 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18 | Umuganwa Diogene (Mine Superintendent) | Pieter Nel (GMM) | Niyitegeka J.Pierre (Mine Superintendent)
TM 04 SOP | Hopper Wagon Tipping | 2024-02-13 | 2024-08-08 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18 | Evode Imena (GM) | Francis Ndawara (Eng Superintendent)
TM 05 SOP | Face Preparation (Misfires and Sockets) | 2024-07-25 | 2024-08-08 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18 |  | Muhirwa Fratani (Mining Engineer)
TM 06 SOP | Entry Examination | 2024-07-26 | 2024-08-08 | 2024-10-15 |  |  |  |  | 90% | Y |  |  | Noel Twagirayeza (Mining Engineer)
TM 07 SOP | Loader Operators- critical items | 2024-08-12 | 2024-08-25 | 2024-10-21 |  |  |  |  | 90% | Y
TM 08 SOP | Marking and Timing Raise | 2024-08-12 | 2024-08-12 | 2024-10-21 | 2024-11-29 | Dusty,Jaco,Faffa,Pieter |  |  | 90% | Y
TM 09 SOP | Marking and Timing- Flat end | 2024-08-12 | 2024-08-12 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18
TM 10 SOP | Bulk Fuel and Lubricant Installations | 2024-08-12 | 2024-08-20 | [5 empty] | 90% | Y
TM 11 SOP | Safe Work Practices - Working at Height | 2024-08-15 | 2024-08-28 | [5 empty] | 90% | Y | 2024-09-18
TM 12 SOP | Dumptruck Operation | 2024-08-16 | 2024-08-28 | [5 empty] | 90% | Y | 2024-09-18
TM 13 SOP | Underground Traffic Management Plan Guideline | 2024-08-16 | 2024-08-28 |  |  |  |  | CODE OF PRACTICE :FATAL RISK CONTROL PROTOCOL | 90% | Y | 2024-09-18
TM 14 SOP | Detection of Flammable Gas | 2024-08-19 | 2024-08-20 | [5 empty] | 90% | Y
TM 15 SOP | Duties and Responsibilities - Mining Suprvisor | 2024-08-19 | 2024-08-24 | 2024-10-25 |  |  |  |  | 90% | Y
TM 16 SOP | Responsibility Limits - Competent A Person (Team Captain) | 2024-08-19 | 2024-08-24 | [5 empty] | 90% | Y
TM 17 SOP | Duties and Responsibilities Mining Section Leaders (Shiftboss) | 2024-08-19 | 2024-08-25 | 2024-10-24 |  |  |  |  | 90% | Y
TM 18 SOP | Wating Place -Symbolic Signs | 2024-08-20 | 2024-08-28 | [5 empty] | 90% | Y
TM 19 SOP | Install and Maintain Barricades | 2024-08-20 | 2024-08-29 | 2024-10-25 | 2024-11-29 | Dusty,Jaco,Faffa,Pieter |  |  | 90% | Y
TM 20 SOP | Typical Symbolic Signs | 2024-08-20 | 2024-09-02 | [5 empty] | 90% | Y
TM 21 SOP | Scraper Winch Installation | 2024-08-20 | 2024-09-02 | [5 empty] | 90% | Y
TM 22 SOP | Holing and Breakthrough Procedure | 2024-08-22 | 2024-09-02 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18
TM 23 SOP | Abandoned Workplaces | 2024-08-22 | 2024-09-02 | 2024-10-14 |  |  |  |  | 90% | Y | 2024-09-18
TM 24 SOP | Heavy Equipment Use Procedure | 2024-08-23 | 2024-09-03 |  |  |  |  | CODE OF PRACTICE :FATAL RISK CONTROL PROTOCOL | 90% | Y
TM 25 SOP | Trackwork Full SOP | 2024-08-23 | 2024-09-03 | [5 empty] | 90% | Y
TM 25a SOP | Trackwork: Install a Rail |  |  | 2024-10-28 | 2024-11-29 | Dusty,Jaco,Faffa,Pieter
TM 25b SOP | Trackwork: Replace a Rail |  |  | 2024-10-28 | 2024-11-29 | Dusty,Jaco,Faffa,Pieter
TM 25c SOP | Trackwork: Install a Switch |  |  | 2024-10-28 | 2024-11-29 | Dusty,Jaco,Faffa,Pieter
TM 25d SOP | Trackwork: Install Jump-Sets |  |  | 2024-10-28
TM 25e SOP | Trackwork: Sliding Rails |  |  | 2024-10-28
TM 25f SOP | Trackwork: Install Permanent Rails |  |  | 2024-10-28
TM 26 SOP | Mono Winch Operators Critical Items | 2024-08-26 | 2024-09-03 | [5 empty] | 90% | Y
TM 27 SOP | Change Management | 2024-08-27 | 2024-09-03 | [5 empty] | 90% | Y | 2024-09-18
TM 28 SOP | Mono Winch Installation | 2024-09-30 | 2024-10-05 | [5 empty] | 0%
TM 29 SOP | Pre-Planning | 2024-09-02 | 2024-09-03 | 2024-11-08 |  |  |  |  | 90% | Y
TM 30 SOP | Planned Task Observation Procedure | 2024-09-02 | 2024-09-03 | [5 empty] | 90% | Y
TM 31 SOP | Conventional mining method – Direction and Grade Procedure | 2024-09-09 | 2024-09-10 | [5 empty] | 90% | Y
TM 32 SOP | Tugger Winch Operation | 2024-09-09 | 2024-09-10 | [5 empty] | 90% | Y
TM 33 SOP | Isolation Lockout Tagging Procedure | 2024-09-09 | 2024-09-11 |  |  |  |  | Already in Place | 100% | Y
TM 34 SOP | Installation Camlok Prop | 2024-09-09 | 2024-09-12 | [5 empty] | 90% | Y
TM 35 SOP | Managers Checklist - Appointments | 2024-09-16 | 2024-09-16 | [5 empty] | 90% | Y
TM 36 SOP | Mine Overseers Monthly Document Control Checklist | 2024-09-16 | 2024-09-16 | [5 empty] | 90% | Y
TM 37 SOP | Systematic Supervision | 2024-09-16 | 2024-09-16 | [5 empty] | 90% | Y
TM 38 SOP | Key Control | 2024-09-17 | 2024-09-17 | [5 empty] | 90% | Y
TM 39 SOP | Incident / Injury Reporting and Investigation | 2024-09-17 | 2024-09-18 |  |  |  |  | Already in Place | 70% | Y
TM 40 SOP | Injury Management Procedure | 2024-09-17 | 2024-09-18 | [5 empty] | 70% | Y
TM 41 SOP | Safety Intensive Care Procedure | 2024-09-17 | 2024-09-18 | [5 empty] | 70% | Y
TM 42 SOP | Lifting Equipment Procedure | 2024-09-17 | 2024-09-18 | 2024-11-08 |  |  |  |  | 70% | Y
TM 43 SOP | Underground Fires and Emergencies | 2024-09-18 | 2024-09-18 | [5 empty] | 70% | Y
TM 44 SOP | Injury Classification | 2024-09-18 | 2024-09-19 | [5 empty] | 70% | Y
TM 45 SOP | Standard Operating Procedure Process | 2024-09-30 | 2024-10-03 | [5 empty] | 70% | Y
TM 46 SOP | Portable Ladders | 2024-09-30 | 2024-10-03 | [5 empty] | 70% | Y
TM 47 SOP | Skid Steer Loader (Bobcat)
TM 48 SOP | Start Up Risk Assessment Procedure
Dusty check