## Sheet1
Weekly Meeting Minutes on Vehicle Repairs & Claims Between Greenleaf and Trinity Metals
| No | Issue Description | Vehicle Plate No. (if any) | Mine Site / Location | Responsible Party | Action/Resolution | Deadline/Date Case reported | Deadline/Date 2 (Updated 17-06-2025) | Deadline/Date 3 (Updated 23-06-2025) | Deadline/Date 4 (Updated 08-07-2025) | Deadline/Date 5 (Updated 15-7-2025) | Status
| 1 | No Control Technique (General Inspection) | RAD804X | Musha | Greenleaf | To be taken to Control Technique | 2025-06-10 |  |  |  |  | ✅ Completed
| 2 | Vehicle not replaced | RAD678X | Musha | Greenleaf | Will find a replacement | 2025-06-13 | 2025-06-17 | 2025-06-17 | 2025-07-08 | 2025-07-15 | Tools will be collected today, a driver who is present at Greenleaf will ensure he gets them
| 3 | Replace Pajeros with pickups | RAC930C | Musha | Emma | Musha replacement on Friday, pending Emma will comfirm with Derrick | 2025-06-13 | 2025-06-17 | 2025-06-27 | 2025-07-09 |  | We will get the replacement for pajero after body painting for RAE269E is completed.
| 4 | Delays in invoice processing | - | All Sites | Greenleaf | Confirmed fixed, won't happen again | - |  |  |  |  | ✅ Completed
| 5 | Poor quality of tyres | - | All Sites | Greenleaf | Will assess tyre quality issue | - |  |  |  |  | ✅ Completed
| 6 | Tyres requested but not received | - | Rutongo & Nyakabingo | Derrick | They will available this week | 2025-06-17 | 2025-06-17 | 2025-06-17 |  |  | Done
| 7 | Police report follow-up | RAD678X | Musha | Aminah | Report to be shared this week | This week | 2025-06-19 |  | 2025-07-09 |  | Completed
| 8 | Emma to stop calling Drivers | - | All Sites | Emma | We agreed that he is supposed to call Fleet Supervisors not Drivers for the things related to fleet | - |  |  |  |  | ✅ Completed
| 9 | Replacement plate needed before body painting | RAI677I | Rutongo | Greenleaf | Service, painting, Technical Inspection (Emma will confirm with Derrick on the replacement for Explosive.) | - | 2025-06-23 | 2025-06-27 | 2025-07-14 | 2025-07-17 | To be realised on 17/7/2025 after body painting
| 10 | Pending payment and missing documents | RAG912G | Rutongo | Greenleaf | To pay traffic fine of 200K, provide missing documents by this week | 2025-06-11 | 2025-06-17 | 2025-06-24 | 2025-07-08 | 2025-07-15 | Derrick to share with us the proof that shows that fine is for Rutongo after the meeting
| 11 | Replacement Plate No RAG356A | RAG356A | Rutongo | Greenleaf | It was sent to greenleaf for repair |  | 2025-06-17 | 2025-06-27 |  |  | Done
| 12 | No Control technique | RAI066S | Rutongo | Greenleaf | Waiting for declaration |  | 2025-06-17 | 2025-06-23 |  |  | Done
| 13 | Engine mount not replaced during repair | RAH036H | Rutongo | Greenleaf | Emma will confirm with Derrick on the replacement . |  |  | 2025-06-23 |  |  | Done
| 14 | Technical Inspection issue with fine of 60K | RAF458V | Rutongo | Greenleaf | Technical Inspection issue with fine of 60K |  |  | 2025-06-24 | 2025-07-08 |  | Done
| 15 | Vehicle lights that were damaged | - | All Sites | Greenleaf | New stock arriving will be available | 2025-06-15 |  | 2025-06-27 |  |  | From Next week lamps will be ready, but we need to have a list of vehicles that have got issues
| 16 | Vehicle lights that were damaged | RAD804X | Musha | Greenleaf | To do service ,fixing back door and to Replace damaged light on Both Sides |  |  | 2025-06-27 |  | 2025-07-16 | To be taken to greenleaf for service
| 17 | Vehicle lights that were damaged | RAG376E | Musha | Greenleaf | To do service and to Replace damaged light on right hand Side and even to give us the missing tools that were not given |  |  | 2025-06-27 |  | 2025-07-18 | To be taken to greenleaf
| 18 | Vehicle lights that were damaged | RAF573S | Musha | Greenleaf | to replace the damaged light on Left hand side and service |  |  | 2025-06-27 |  | 2025-07-17 | To be taken to greenleaf
| 20 | Vehicle lights that were damaged | RAE656X | Musha | Aminah | Left hand side |  |  | 2025-06-27 | 2025-07-08 | 2025-07-22 | To be sent to Greenleaf to fix the damaged lights next week
| 21 | Vehicle lights that were damaged | RAE269E | Musha | Greenleaf | Both Sides, and body painting, seat covers |  |  | 2025-06-27 | 2025-07-09 |  | it was sent to greenleaf on 11/7/2025 for body painting and to fix the seats and to replace the damaged lights on right hand side .Emma to confirm when to be returned
| 22 | Vehicle lights that were damaged | RAE051P | Nyakabingo | Joel | Right Hand Side |  |  | 2025-06-27 |  |  | This vehicle hasn't been sent to greenleaf for replacing the damaged lights
| 23 | Vehicle lights that were damaged | RAF251V | Nyakabingo | Greenleaf | Right Hand Side |  |  | 2025-06-27 |  |  | This vehicle hasn't been sent to greenleaf for replacing the damaged lights
| 24 | Vehicle lights that were damaged | RAI677I | Rutongo | Greenleaf | Both Sides |  |  | 2025-06-27 |  |  | This vehicle hasn't been sent to greenleaf for replacing the damaged lights,Fleet to start sending them for repair
| 25 | Vehicle lights that were damaged | RAG912G | Rutongo | Greenleaf | Left hand side |  |  | 2025-06-27 | 2025-07-09 |  | This vehicle hasn't been sent to greenleaf for replacing the damaged lights,Fleet to start sending them for repair
| 26 | Vehicle lights that were damaged | RAG190H | Rutongo |  | Both Sides |  |  | 2025-06-27 |  |  | This vehicle hasn't been sent to greenleaf for replacing the damaged lights,Fleet to start sending them for repair
| 27 | Drivers Training for the defensive Driving | All Drivers | All Sites | Greenleaf/Trinity Logistics | Greenleaf to share the plan for July | 2025-07-01 |  | TBC | 2025-07-15 |  | Greenleaf to share the 2 different weekend program plan by end of this week Friday 18th July 2025