## Instructions
Instructions:
- The header includes a Site dropdown (Nyakabingo / Rutongo / Musha) in cell F2 so the same template can be used for all three sites.
- Reflect all possible risk events as possible considering your area of operations (ECC logic (Risk Event, Cause, Consequence, Existing Controls))
- Enter Likelihood, Impact and Control ratings using the dropdowns; Risk Score, Risk Rating, Residual Risk and Residual Rating are calculated automatically.
- The Residual Risk uses a simple control-adjusted formula: Residual ≈ Risk Score × (1 − (avg control effectiveness)).
- Dashboard counts are populated automatically and the sheet includes a pie chart.

## Risk Register
Trinity Metals Ltd – Pre-Workshop Risk Assessment (2025)
|  |  | Department: Supply Chain (Procurement & Store and Fleet) |  |  |  | Site:
Primary Risk Owner: Procurement and Fleet Supervisors
Group Link: Group Supply Chain Manager
No | Risk_ID | Process | Risk Event | Cause | Consequence | Existing Controls | Likelihood (1-5) | Impact (1-5) | Risk Score (Auto) | Risk Rating (Auto) | Control Design (1-5) | Control Implementation (1-5) | Control Operating (1-5) | Residual Risk (Auto) | Residual Rating (Auto) | Mitigation Action | Owner | Target Date | KPI Reference | Comments | Risk Category
1 | MSH-SCM-001 | Planning | Poor demand forecasting | Inaccurate consumption data | Stockouts and delivery delays | Manual planning of requirements | 5 | 5 | 25 | Moderate | 3 | 1 | 1 | 17 | High | Implement automated demand forecasting | Heads of Departments | Q2 | Forecast accuracy % | SCM SOP | Operational
2 | MSH-SCM-002 | Stock Reordering | Late replenishment | Slow approval process | Stockouts | Fast-track approval process | 4 | 5 | 20 | Moderate | 3 | 1 | 1 | 13 | Moderate | Auto alerts for reorder levels | Management | Q2 | Stockout rate | SCM System | Operational
3 | MSH-SCM-003 | Vendor Payments | Late supplier payments (advance) | Limited payment batches | Disruption of operations | Payment plan review | 4 | 4 | 16 | Moderate | 3 | 3 | 1 | 9 | Moderate | Supplier payment portal | Finance | Q4 | Payment timeliness | Finance Policy | Operational
4 | MSH-SCM-004 | Purchasing | Market price fluctuation | Lack of long-term contracts | Cost instability and supply risk | Strategic sourcing policy | 5 | 5 | 25 | Moderate | 3 | 1 | 1 | 17 | High | Enforce long-term contracts | Group Procurement Superintendent | Q1 | Cost variance | SC Policies | Compliance
5 | MSH-SCM-005 | Maintainance | Company Light vehicle / HME breakdown | Poor or delayed maintenance | Frequent breakdowns and downtime | Planned Preventive Maintenance (PPM) | 5 | 5 | 25 | Moderate | 2 | 1 | 1 | 18 | High | Enforce maintenance schedules | Engineering | Q1 | Equipment availability % | Engineering SOP | Operational
6 | MSH-SCM-006 | Incident | Light vehicle / HME incident | Poor driving skills and maintenance | Safety incidents, high cost, downtime | Operator competency checks | 3 | 3 | 9 | Moderate | 3 | 2 | 2 | 5 | Low | Increase driver & operator training | Fleet Supervisor | Q1 | Incident rate | Fleet SOP | Operational
7 | MSH-SCM-007 | Purchasing | Delay of international orders | Long PR-to-PO cycle and production lead time | Operational disruption | PR monitoring | 5 | 5 | 25 | Moderate | 3 | 2 | 2 | 13 | Moderate | Group Procurement escalation | Group Procurement Superintendent | Q2 | PR–PO cycle time | GPS escalation | Compliance
8 | MSH-SCM-008 | Poor planning | Keeping non-stock items | Poor planning or project delays | High holding cost | Requirement planning | 5 | 5 | 25 | Low | 4 | 1 | 1 | 15 | High | Enforce approval for non-stock items | HODs | Q2 | Non-stock value | SCM Policy | Operational
9 | MSH-SCM-009 | Incident | Snakes in main store | Bushes and poor housekeeping | Safety risks and injuries | Periodic cleaning | 3 | 4 | 12 | Moderate | 3 | 1 | 1 | 8 | Moderate | Clear bushes & improve housekeeping | SHEC | Q1 | Safety incidents | HSE SOP | Safety
10 | MSH-SCM-010 | Inventory Management | Stock variance | Incorrect packing of orders | Inventory inaccuracy and losses | Manual checks | 2 | 3 | 6 | Moderate | 3 | 1 | 1 | 4 | Low | Pick & pack verification system | Group Procurement Superintendent | Q2 | Stock variance % | Warehouse SOP | Operational

## Dashboard
Supply Chain (Procurement & Fleet) - Summary Dashboard
Counts by Risk Rating (Risk Rating column H)
Low | 1
Moderate | 9
High | 0
Critical | 0