## SOW Timeline
| March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September
Activity | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Land use maps for each CA (GIS mapping)
Groundtruthing GiS Mapping | bar: March 1 to April 4
Final Baseline Status Quo Reports each CA
SEP Meeting - Rulindo | bar: March 2
SEP Meeting - Rwamagana
Needs Assessment - Rutongo | bar: March 1 to April 4
Needs Assessment - Musha
Needs Assessment - Nyakabingo | bar: May 1 to June 4
Draft LED plans - Rutongo
Draft LED plans - Musha | bar: June 1 to July 5
Draft LED plans - Nyakabingo
Finalize LED Plans - Rutongo | bar: July 1 to August 4
Finalize LED Plans - Musha
Finalize LED Plans - Nyakabingo | bar: July 1 to August 4
DFC Gap Analysis
LED Implementation Plan - Rutongo | bar: August 1 to September 5
LED Implementation Plan - Musha
LED Implementation Plan - Nyakabingo | bar: August 1 to September 5