## SOW, Budget and Schedule (hidden)
# | Activity | # | Tasks | Phase | Status | Service Provider | Deliverables | TMG Co-spend | TA Budget | Milestone Payment No. | Q2 '24 | Q3 '24 | Q4 '24 | Q1 '25 | Q2 '25 | Q3 '25
1 | Trinity Metals Group Skills Training and People Development | 1.1 | Full Training Needs Assessment and Analysis across the Trinity Group. | 1 | Completed | SML4 Change | 1.1.1. Organisational Training needs assessment & analysis : Report 1.1.2. Organisational Training needs assessment and Analysis: Plan | 32000 |  | MP 1
|  | 1.2 | Development and delivery of a leadership program for all Supervisors and Managers. | 1 | 1. Training Programmes Developed for Supervisory, Management and Leadership levels in three Phases - A, B and C:
|  | (i) | Design and Implement learning Solutions: Part A | 1 | In Progress | SML4 Change | 1.2.i.1. Training architecture & learning solutions delivery 1.2.i.2. Supervisory program training package 1.2.i.3. Leadership program training package 1.2.i.4. Management Development program 1.2.i.5.Graduate Development program 1.2.i.6.Service/Support Depts. Training system |  | 80000 | MP 2 | 80000
|  | (ii) | Design and Implement learning Solutions: Part B | 1 | Not started | SML4 Change | 1.2.ii.1.Supervisory coaching program 1.2.ii.2.Mentorship program 1.2.ii.3. Team Training Program |  | 80000 | MP 3 |  | 80000
|  | (iii) | Monitoring and Review | 1 | Not started | SML4 Change | 1.2.iii.1. Learning & skills workplace application 1.2.iii.2. Skills Program Development |  | 100000 | MP 3 |  | 100000
|  | 1.3 | Development of a formal Training Function and System with Rwandan Trainers for the Trinity Group (Training Governance and System Tools). | 1 | In Progress | SML4 Change | 1.3.1. Organisational training System 1.3.2. Training support systems | 75000 |  | ??
|  | 1.4 | Development and implementation of formal blasting training certification | 1 | In Progress | SML4 Change | 1.4.1. Blasting certificate training program 1.4.2. Pilot Session 19-Feb - 8 March 2024. 1.4.3. National Certification |  | 30000 | MP 2 | 30000
|  | 1.5 | Development and implementation of competency-based training programs for all critical jobs, prioritizing high risk equipment and machinery training. | 1 | In Progress | SML4 Change | 1.5.1. Hazard Identification & Risk Assessment (HIRA) program developed for all employees. 1.5.2. Technical programs for Mining, Engineering & Process to commence |  | 50000 | ?? | 50000
|  | 1.6 | English and Communications Skills Training | 2 | Not started | HULT / EF | 1.6.1. 320 employees complete Teacher-led English & Communication Program |  | 300000 | MP 5 & 6 |  | 100000 |  | 100000 |  | 100000
|  | 1.7 | English Proficiency testing | 2 | Not started | HULT / EF | 1.7.1. English proficiency testing for 4000 employees |  | 60000 | MP 4, 5 & 6 |  |  | 20000 |  | 20000 | 20000
| Trinity Metals - Cost Share | 25% of Project budget : Internal Trinity HR training staff salaries, use of facilities, catering, accommodation and transportation of trainees, | [5 empty] | 175000 |  |  | NOTES:
|  | Additional Costs for SML consultants (Flights, transport and accommodation etc) | [5 empty] | 60000
|  | Training/skills development costs (programs, courses, seminars, study assistance etc) | [5 empty] | 100000
|  | NEBOSH training | [5 empty] | 20000
|  | Safety Training - mine rescue setup and training | [5 empty] | 60000
|  | Finance and HR Training | [5 empty] | 60000
|  | MARY - please indicate additional funding | [5 empty] | 118000
| TOTAL FOR A | [6 empty] | 700000 | 700000 |  | 160000 | 280000 | 20000 | 100000 | 20000 | 120000
2 | Development and Implementation of an integrated, group-wide SHEC Management System. | 2.1 | Gap Analysis. Review of all SHEC system procedures, registers and records, identification of gaps and design program for SHEC system development and implementation. | 1 | Completed | GF & JLD | 2.1.1. Gap analysis, plan and programme for implementation of the SHEC MS | 30000 |  | MP 1
|  | 2.2 | Baseline-Risk Assessment and Impact/Aspect Register for all operations and activities, undertaking the necessary training of SHEC and operational staff. | 1 | In progress | GF & JLD | 2.2.1. Baseline Risk Assessment for all activities across the entire TMG group. (MP 1) 2.2.2. Training of SHEC staff and supervisors in BLRA procedure. (MP 2) 2.2.3. Impact/Aspect Register for Group and for each of the Mines (MP 2) | 25000 | 20000 | MP 1, 2 |  | 20000
|  | 2.3 | Engineering/structural analyses for underground workings and tailings/waste piles and dams. | 1 | In progress | OHMS / TS/ Bara | 2.3.1. Engineering / structural reporting | 20000 | 80000 | MP 1 | 40000 |  | 40000
|  | 2.4 | Baseline OH Surveys for all OH risk-exposure working areas (include: vibration, noise, ventiliation, dust, light and ergonomic, gasses etc) | 1 | not started | tbc | 2.4.1. OHS Baseline Survey results and recommendations |  | 60000 | MP 3 |  |  | 60000
|  | 2.5 | Setting of the SHEC Targets and Objectives at a corporate level and across all mining operations | 2 | Completed for Trinity for 2024 | GF & JLD | 2.5.1. SHEC targets and objectives for 2024 (completed). (MP 1) 2.5.2. SHEC Targets and objectives for 2025. (MP 4) | 20000 | 10000 | MP 1, 4 |  |  |  | 10000
|  | 2.6 | SHEC System procedure development, covering all elements related to ISO 14001: 2015 and ISO 45001: 2018. | 2 | In progress | GF & JLD | 2.6.1. All SHEC System Procedures developed. | 15000 | 40000 | MP 3 |  | 20000 |  | 20000
|  | 2.7 | Operational Environmental and Social Action Plan (ESAP), aligned to the ESIA, Impact Aspect register, legal register and lender requirements. | 2 | In progress (highlevel for TMG completed) | GF & JLD | 2.7.1. Highlevel TMG ESAP (completed and updated regularly. (MP 1) 2.7.2. ESAPs for each of the Mines. (MP 4) 2.7.3. Lender ESAP (not in TAIP) |  | 20000 | MP 1, 4 |  |  |  | 20000
|  | 2.8 | Implementation of the SHEC System Procedures. | 2 | In progress | GF & JLD | 2.8.1. All SHEC procedures implemented, necessary training in their application undertaken. |  | 30000 | MP 4 |  |  |  | 30000
|  | 2.9 | Training and Mentoring of management and SHEC personnel in the MS implementation. | 2 | In progress | GF & JLD | 2.9.1. SHEC staff able to fulfil their functions effectively. |  | 60000 | MP 4? |  |  |  | 30000 | 30000
|  | 2.1 | 1st Aid (Level 1 and 2) and 1st responder training and refresher training across TMG | 2 | In progress | tbc | 2.10.1. Courses completed and registers maintained. |  | 20000 | MP 4 |  |  |  | 20000
|  | 2.11 | Behavior Based Care (BBC) System development and implementation | 2 | not started | tbc | 2.11.1. BBC System Planning Document. 2.11.2. BBC training records and reporting |  | 60000 | MP 5 |  |  |  | 30000 |  | 30000
| Trinity Metals - Cost Share (B) | 25% of Project Budget: HSE Staff salaries and expenses, transportation costs, hygiene surveys, H&s campaigns etc | [5 empty] | 75000 |  |  | NOTES:
|  | Additional consulting fees for OHS and E&S Specialists | [5 empty] | 60000 |  |  | GF - Gerrit Ferriera ; JLD: Joanne Daneel
|  | Mobile Equipment Driver/Operator training | [5 empty] | 30000 |  |  | OHMS - Open House Management Solutions (Geotech inspections, advice and reporting)
|  | Medical Serveillance Programme | [5 empty] | 60000 |  |  | TS - Tailings Solutions (Tailings design and assessment - dam design and assessment - competent persons reporting )
|  | PPE Provision | [5 empty] | 35000 |  |  | Bara Consulting - Mining Engineering
|  | OHS Monitoring Equipment | [5 empty] | 30000
| TOTAL FOR B | [6 empty] | 400000 | 400000 |  | 40000 | 40000 | 100000 | 160000 | 30000 | 30000 | 400000
3 | Formulation of an Integrated Development Plan (IDP) for the Concessions. | 3.1 | Comprehensive GIS-based Land Use Mapping of all the Trinity Metals Concession areas, utilizing latest Satellite Imagery. | 1 | In Progess | SLR / In country GIS sevices | 3.1.1. Accurate, groundtruthed geo-referenced mapping for all three Trinity Mining Concessions . Map will include: 1. Landuses (mining, agriculture etc), 2. land condition (degration, erosion etc) 3. topographical features (rivers, wetlands, steep slopes)..etc |  | 60000 | MP 3 | 60000
|  | 3.2 | Ground truth landuse/ landcover data, key social institutions and activities, land condition, river and wetland drivers etc. | 1 | Not started | TB / JK / GT |  |  | 120000 | MP 3 |  | 60000 | 60000
|  | 3.3 | Stakeholder engagement in all phases for the IDPs and at all levels (initiation, needs and opportunities, Draft IDPs etc) | 1 | Not started | TB / JK / MB | 3.3.1. Stakeholder Database (MP 2) 3.3.2. Stakeholder Engagement Plan (MP 2) 3.3.3. Engagement documentation (workshop outcomes, meeting minutes etc) (MP 4) |  | 120000 | MP 2 & 4 | 40000 |  | 40000 |  | 40000
|  | 3.4 | Needs analysis and livelihood assessment for each of the concessions based on a RRA (rapid rural appraisal) approach | 1 | Not started | TB / JK / MB | 3.4.1. Needs analysis and livelihood assessment report - for each concession. |  | 60000 | MP 4 |  |  |  | 60000
|  | 3.5 | Sustainable livelihood development plans for each concession | 1 | Not started | TB / JK / MB | 3.5.1. Sustainable Livelihood Development Plans for each concession |  | 60000 | MP 5 & 6 |  |  |  | 60000
|  | 3.6 | Drafting of a Sustainable Integrated Development Plans (IDPs) and Programs for the Concession Areas | 2 | Not started | TB / JK / MB | 3.6.1. SIDP for each concession. |  | 300000 | MP 5 & 6 |  |  |  |  | 300000
|  | 3.7 | Funding model for the implementation of the IDPs through potential partnerships with government, funding agencies and the private sector. | 2 | Not started | TB / MB | 3.7.1. Funding model and proposals |  | 60000 | MP 6 | [5 empty] | 60000
|  | 3.8 | Develop a performance monitoring system to link with UN SDG’s. | 2 | Not started | MB | 3.8.1. Performance monitoring system |  | 20000 | MP 6 | [5 empty] | 20000
| Trinity Metals - Cost Share (C) | 25% of Project budget : CLO salaries, Casual staff salaries, tree planting, terracing | [5 empty] | 200000 |  |  | NOTES:
|  | Purchase of Satellite Imagery, elevation data and lidar survey's | [5 empty] | 50000 |  |  | TB - Tony Barbour (social consultant for the ESIA SIA) - www.tonybarbour.co.za
|  | Anchor Community Project in each of the concession areas (e.g water supply upgrade) | [5 empty] | 150000 |  |  | JK - Justus Kangwagye (Community liaison and stakeholder consultant - in country)
|  | ECDC Support in all three concession areas | [5 empty] | 80000 |  |  | GT - Groundtruth Consulting (aquatic and terrestrial environmental engineering. www.groundtruth.co.za)
|  | Maintanace of Community Roads (ad hoc) | [5 empty] | 60000 |  |  | MB - Martina Bennett (social scientist)
|  | Community Service (Umuganda) | [5 empty] | 50000
|  | Medical contributions to vulnerable people | [5 empty] | 60000
|  | Other community Development and CSR costs | [5 empty] | 150000
| TOTAL FOR C | [6 empty] | 800000 | 800000 |  | 100000 | 60000 | 100000 | 120000 | 340000 | 80000 | 800000
4 | The Development of a Legacy Tailings Management and River Rehabilitation Plan for Rutongo, Musha and Nyakabingo Concessions | 4.1 | Baseline Assessment for all mining concessions of the affected rivers, and sources of contamination in and adjacent to affected rivers and preferred pathways of surface water runoff, to determine the river health (present ecological health) and assess river and wetland system drivers. Assessments to include full characterization of waste material, surface water and sediments | 1 | In progress | AB / GT / TS | Baseline Assessments: 4.1.1. Mapping of potential sources of Contaminants (MP 2) 4.1.2. Legacy Tailings mapping, and quantification (MP 2) 4.1.3. Geochem Assessment (waste materials and sediments) (MP 2) 4.1.4. Determination of the PES of all the river systems (MP 3) 4.1.5. Waste characterisation (MP 2) |  | 200000 | MP 2, 3 | 100000 | 100000
|  | 4.2 | Desktop mapping and GIS analysis. | 1 | Not started | GT / tbc | 4.2.1. Mapping of all sources and receptors of contamination and GIS Analysis |  | 60000 | MP 3 |  | 60000
|  | 4.3 | Floodline determination for each of the concession areas, including projected flood events under climate change scenarios. | 1 | Not started | GT | 4.3.1. Floodlines Determination Report |  | 40000 | MP 4 |  |  | 40000
|  | 4.4 | Catchment hydrological modelling to characterize present water flows and potential future changes. | 1 | Not started | GT | 4.4.1. Catchment hydrological models |  | 100000 | MP 4 |  |  | 100000
|  | 4.5 | Review and assessment of GAP analysis of Phase 1. | 2 | Not started |  | 4.5.1. Gap Analysis Report |  | 20000 | MP 4 |  |  |  | 20000
|  | 4.6 | Additional data collection, analysis and reporting as recommended by DFC to address gaps identified in Phase I of this task. | 2 | Not started | SLR / GT / TS | 4.6.1. tbc |  | 80000 | ? |  |  |  | 80000
|  | 4.7 | Feasibility studies for all mining concessions including comparative analyses of options for mineral recovery from legacy tailings, and remediation of waste sources and areas of contamination. | 2 | Not started | TS / GT / GB / ETEK | 4.7.1. Legacy Tailings management and recovery feasibility study reports for each mine / mining area. |  | 250000 | MP 5 |  |  |  |  | 200000
|  | 4.8 | Scenario modelling and determination of management strategies and interventions required to restore rivers and wetlands to a predetermined ecological state to maximize climate resilience | 2 | Not started | TS / GT / ??? | 4.8.1. River rehabilitation scenario modelling and reporting. |  | 200000 | MP 5 | [5 empty] | 200000
|  | 4.9 |  |  |  |  | 4.9.1. Integrated tailings Management and River Rehabilitation Plan and Programme for each Concession |  | 230000 | MP 6
| Trinity Metals - Cost Share (D) | 25% of Project budget : In kind: Tech Services salaries and expenses etc | [5 empty] | 237500 |  |  | NOTES:
|  | Additional consulting fees from Tailings Engineers (TAILINGS SOLUTIONS) for the design of engineered and GIIP-compliant tailings facilities | [5 empty] | 400000 |  |  | AB: Andrea Baker (Geochemist with SLR) GT: GroundTruth Consulting
|  | Additional consulting fees from Mineral Processing Consultants | [5 empty] | 150000 |  |  | TS - Tailings Solutions (Tailings design and assessment - dam design and assessment - competent persons reporting )
|  | Mine Rehabilitation and closure quantification (ETEK) | [5 empty] | 162500 |  |  | ETEK - ETEk consulting (mine closure and rehabilitation specialists). Greg Brooker (Mineral Process Engineer)
| TOTAL FOR D | [6 empty] | 950000 | 1180000 |  | 100000 | 160000 | 140000 | 100000 | 200000 | 200000 | 900000
5 | Preliminary Assessment/Site Inspections for all three of the TMG mines (Rutongo, Nyakabingo and Musha) | 5.1 | Preliminary Assessment/Site Inspections for an estimated 9 separate mine sites in three mining concessions (7 separate sites at the Rutongo concession), including the following components: | 1 | In progress | SLR | 5.1.1. Inception Report 5.1.2. Gap Analysis Report. 5.1.3. Baseline Specialist Reports: 1. Geohydrology (report and modelling) 2. Hydrology (report, water balances and stormwater management plans) 3. Cultural Heritage 4. Air Quality. 5. Noise 6. Climate Change Assessment 7. Human Rights Assessment 8. Social Impact Assessment 9. Geochem assessment 10. Aquatic Biodiversity | 150000 | 75000 | MP 1 | 75000
|  | 5.2 | Characterization of mine waste sources, ambient air, soil, groundwater surface water and sediment; | 1 | In progress | SLR |  | 150000 | 100000 | MP 1 | 100000
|  | 5.3 | Analysis of hydrogeology; identification of ecological and human receptors with an analysis of potential impacts to these receptors from existing contamination and contaminant migration. | 1 | In progress | SLR | 5.3.1. Environmental and Social Impact Assessment Reports for each mine. |  | 300000 | MP 2 & 3 | 250000 | 50000
|  | 5.4 | Review and assessment of GAP analysis of Phase 1. | 2 | Not started |  | 5.4.1. Gap Analysis Report |  | 40000 | MP 4 |  |  | 40000
|  | 5.5 | Additional data collection, analysis and reporting as recommended by DFC to address gaps identified in Phase I of this task. | 2 | Not started | tbc | 5.5.1. tbc |  | 500000 | MP 5 |  |  |  | 200000 | 200000 | 100000
| Trinity Metals - Cost Share (E) | 25% of the Project Budget: E&S Staff salaries, transport, expenses etc) | [5 empty] | 250000
|  | Drillings of boreholes (Africa Drilling) | [5 empty] | 125000
|  | Additional Geohydrology consulting fees and dewatering boreholes (SLR) | [5 empty] | 65000
|  | Water, Air quality, noise monitoring and reporting (21 months) | [5 empty] | 85000
|  | Purchase of monitoring equipment | [5 empty] | 60000
|  | Pollution control dam - Nyakabingo | [5 empty] | 40000
|  | New pollution control dam - Rutongo; Karambo river rehabilitation and bank protection | [5 empty] | 90000
| TOTAL FOR E | [6 empty] | 1015000 | 1015000 |  | 425000 | 50000 | 40000 | 200000 | 200000 | 100000 | 1015000
GRAND TOTAL | [7 empty] | 3865000 | 4095000 |  | 825000 | 590000 | 400000 | 680000 | 790000 | 530000
(MOBILISATION)
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this supposed to be cost-share? It is in the TAIP payment schedule for these two deliverables.
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MP 2 for Activity 1 is supposed to be $128,000
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It seems like all of these deliverables were submitted for MP 1? But the names of the deliverables don’t completely align.
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Paramedic training? $140K per year
Note on J22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This doesn’t align with the MP 2 amount in the TAIP (which is for $40K for 2.2.2 and 2.2.3 only)
Note on J23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Look into increasing this amount to $100K
Note on J24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs $80K Reply: Gerrit says it should be $40K
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This does not appear in the TAIP - is it part of deliverable 2.8.1?
Note on D30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be moved to TA1
Note on J31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is only $30K in the TAIP. Reply: Needs $65K Reply: Gerrit says it should be $75K
Note on I34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should go under Activity 1
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this still be included?
Note on I35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be $80K
Note on I36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could be increased
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider adding a local market assessment (for identifying local procurement opportunities)
Note on J39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does not match the TAIP which has these two deliverables at $160K
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The deliverable “Detailed SOW, R&R and Programme for the IDPs”, which is included in MP 2 in the TAIP, is missing from this Budget.
Note on H43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can 3.5 and 3.6 be merged? Aren’t they the same thing?
Note on J46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MP 5 & 6 should add up to $430K per the TAIP, but here it’s $440K
Note on D56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would include input from Koos (tailings) and Greg (mineral processing), as well as GroundTruth (river health) and Andrea Baker (SLR - Geochemistry)
Note on G57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might have SLR support this
Note on K61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not in TAIP milestone payment schedule
Note on J62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The total payment for MP 5 for these two deliverables is only $300K per the TAIP
Note on H64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a deliverable in the TAIP, but wasn’t included here in this Budget.
Note on J70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The TAIP MP schedule has 5.1. and 5.2’s payment for $260K (not $175K)
Note on J72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The total for MP 2 & 3 is$215K in the TAIP
Note on K72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should all go into MP 2
Note on H74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: “Additional Baseline Studies as defined by Gap Analysis” is the deliverable in the TAIP

## Revised Budget (hidden)
[11 empty] | 2024-06-01 | 2024-08-01 | 2025-01-01 | 2025-04-01 | 2025-09-01 | 2026-01-01 | 2026-05-01
# | Activity | # | Tasks | Phase | Status | Service Provider | Deliverables | TMG Co-spend | TA Budget | Milestone Payment No. | Mobilization Payment | MP 1 | MP 2 | MP 3 | MP 4 | MP 5 | MP 6
1 | Trinity Metals Group Skills Training and People Development | 1.1 | Full Training Needs Assessment and Analysis across the Trinity Group. | 1 | Completed | SML4 Change | 1.1.1. Organisational Training needs assessment & analysis : Report |  | 16000 | MP 1 |  | 16000
|  |  |  | 1 | Completed | SML4 Change | 1.1.2. Organisational Training needs assessment and Analysis: Plan |  | 16000 | MP 1 |  | 16000
|  | 1.2 | Development and delivery of phase 1 training programs - leadership program for all Supervisors and Managers, competency-based training, blasting certificate program, formal training function (ToT), etc. | 1 | Completed | SML4 Change | 1.2.1. Monthly progress reports and supporting documentation for the delivery of phase 1 training programs (Part A) | 27154.91 | 80000 | MP 1 |  | 80000
|  |  |  | 1 | In Progress | SML4 Change | 1.2.2. Monthly progress reports and supporting documentation for delivery of phase 1 training programs (Part B) |  | 276000 | MOB & MP 2 | 176000 |  | 100000
|  | 1.3 | Development and implementation of phase 2 training programs focused on Coaching and Mentoring, Compliance, Safety, etc. and continuation of some phase 1 training programs (technical training, formal training structure, leadership training, etc) | 2 | not started | SML4 Change | 1.3.1. Monthly progress reports and supporting documentation for phase 2 training programs (Part A) |  | 130000 | MP 3 |  |  |  | 130000
|  |  |  | 2 | not started | SML4 Change | 1.3.2. Monthly progress reports and supporting documentation for phase 2 training programs (Part B) |  | 130000 | MP 4 |  |  |  |  | 130000
|  |  |  | 2 | not started | SML4 Change | 1.3.3. Monthly progress reports and supporting documentation for phase 2 training programs (Part C) |  | 27000 | MP 5 | [5 empty] | 27000
|  | 1.4 | Development and implementation of E-learning Platform | 2 | not started | SML4 Change | 1.4.1. E-learning platform |  | 25000 | MP 5 | [5 empty] | 25000
|  | 1.5 | First responder training (paramedics) | 2 | not started | tbc | 1.5.1. 1st responder training completion report | 60000 |  | MP 4 |  |  |  |  | 0
| Trinity Metals - Cost Share | 25% of Project budget : Internal Trinity HR training staff salaries, use of facilities, catering, accommodation and transportation of trainees | [5 empty] | 175000
|  |  | Taxes WHT and VAT (28% of external consultant fees) |  |  |  |  | 194409
|  | Additional Costs for SML consultants (Flights, transport and accommodation etc) | [5 empty] | 60000
|  | Trinity-funded 2025 Training | [5 empty] | 215093
|  | Trinity-funded 2026 Training | [5 empty] | 90268
| TOTAL FOR A1 | [6 empty] | 821924.91 | 700000 | should be 700K | 176000 | 112000 | 100000 | 130000 | 130000 | 52000 | 0
2 | Development and Implementation of an integrated, group-wide SHEC Management System. | 2.1 | Gap Analysis. Review of all SHEC system procedures, registers and records, identification of gaps and design program for SHEC system development and implementation. | 1 | Completed | GF & JLD | 2.1.1. Gap analysis, plan and programme for implementation of the SHEC MS | 40000 | 30000 | MP 1 |  | 30000
|  | 2.2 | Baseline-Risk Assessment and Impact/Aspect Register for all operations and activities, undertaking the necessary training of SHEC and operational staff. | 1 | In progress | GF & JLD | 2.2.1. Baseline Risk Assessment for all activities across the entire TMG group. (MP 1) | 20000 | 15000 | MP 1 |  | 15000
|  |  |  | 1 | In progress | GF & JLD | 2.2.2. Training of SHEC staff and supervisors in BLRA procedure. |  | 10000 | MP 2 |  |  | 10000
|  |  |  | 1 | In progress | GF & JLD | 2.2.3. Impact/Aspect Register for Group and for each of the Mines |  | 10000 | MP 3 |  |  |  | 10000
|  | 2.3 | Engineering/structural analyses for underground workings and tailings/waste piles and dams. | 1 | In progress | OHMS / ETS | 2.3.1.Engineering Structure Reports for all the mines | 20000 | 20000 | MP 1 |  | 20000
|  |  |  | 1 | not started | OHMS / ETS | 2.3.2. Additional quarterly engineering structure reports for all the mines |  | 90000 | MP 2-5 |  |  | 25000 | 25000 | 20000 | 20000
|  | 2.4 | Baseline OH Surveys for all OH risk-exposure working areas (include: vibration, noise, ventiliation, dust, light and ergonomic, gasses etc) | 1 | Q1 2025 | tbc | 2.4.1. OHS Baseline Survey results and recommendations |  | 40000 | MP4 |  |  |  |  | 40000
|  | 2.5 | Setting of the SHEC Targets and Objectives at a corporate level and across all mining operations | 2 | Completed for Trinity for 2024 | GF & JLD | 2.5.1. SHEC targets and objectives for 2024 (completed) | 10000 | 5000 | MP 1 |  | 5000
|  |  |  | 2 | Completed for Trinity for 2024 | GF & JLD | 2.5.2. SHEC Targets and objectives for 2025. |  | 5000 | MP 2 |  |  | 5000
|  | 2.6 | SHEC System procedure development, covering all elements related to ISO 14001: 2015 and ISO 45001: 2018. | 2 | In progress | GF & JLD | 2.6.1. All SHEC System Procedures developed. |  | 30000 | MP 3 |  |  |  | 30000
|  | 2.7 | Operational Environmental and Social Action Plan (ESAP), aligned to the ESIA, Impact Aspect register, legal register and lender requirements. | 2 | In progress (highlevel for TMG completed) | GF & JLD | 2.7.1. Highlevel TMG ESAP (completed and updated regularly. |  | 10000 | MP 1 |  | 10000
|  |  |  | 2 | In progress (highlevel for TMG completed) | GF & JLD | 2.7.2. ESAPs for each of the Mines. |  | 10000 | MP 4 |  |  |  |  | 10000
|  | 2.8 | Implementation of the SHEC System Procedures. | 2 | In progress | GF & JLD | 2.8.1. Internal audit report on SHEC management system implementation |  | 10000 | MP 4 |  |  |  |  | 10000
|  | 2.9 | Training and Mentoring of management and SHEC personnel in the MS implementation. | 2 | In progress | GF & JLD | 2.9.1. External audit report on SHEC management system implementation |  | 40000 | MP 5 | [5 empty] | 40000
|  | 2.1 | Behavior Based Care (BBC) System development and implementation | 2 | not started | tbc | 2.10.1. Behavior Based Care (BBC) System development and implementation |  | 75000 | MP 5 | [5 empty] | 75000
| Trinity Metals - Cost Share (B) | 25% of Project Budget: HSE Staff salaries and expenses, transportation costs | [5 empty] | 75000
[7 empty] | Taxes WHT and VAT (28% of JLD and OHMS) | 100000
|  | Purchase Ambulances for each of the mines | [5 empty] | 288000
|  | Purchase of INX in control | [5 empty] | 40000
|  | Medical Surveillance Programme | [5 empty] | 183000
|  | PPE Provision | [5 empty] | 547346
| TOTAL FOR B | [6 empty] | 1323346 | 400000 | Should be 400K | 0 | 80000 | 40000 | 65000 | 80000 | 135000 | 0
3 | Formulation of the Community Development Plans (CDPs) for the Concessions. | 3.1 | Develop detailed SOW, R&R and Programme for the CDPs | 1 | In Progess | TB / JK/ MB | 3.1.1. Detailed SOW, R&R and Programme for the IDPs |  | 30067 | MP 2 | 16267 |  | 13800
|  | 3.2 | Development of a Stakeholder Database and Engagement Plan | 1 | In Progess | TB / JK/ MB | 3.2.1. Stakeholder Database and Engagement Plan |  | 33603 | MP 3 |  |  |  | 33603
|  | 3.3 | Baseline review and analysis for all three concessions, including land use mapping | 1 | Not started | TB / JK / MB | 3.3.1. Draft Status Quo Reports |  | 20470 | MP 3 |  |  |  | 20470
|  |  |  | 1 | In Progess | SLR / In country GIS sevices | 3.3.2. Detailed landuse maps for each of the concessions (GIS mapping) |  | 69000 | MP 3 |  |  |  | 69000
|  |  |  | 1 | Not started | TB / JK / MB | 3.3.3. Final Status Quo Reports |  | 19550 | MP 3 |  |  |  | 19550
|  | 3.4 | Needs analysis and livelihood assessment for each of the concessions | 1 | Not started | TB / JK / MB | 3.4.1. Concession Community Needs Analysis and Livelihoods Assessment Reports |  | 32200 | MP 4 |  |  |  |  | 32200
|  | 3.5 | Drafting of the Community Development Plans for each concession | 1 | Not started | TB / JK / MB | 3.5.1. Draft Community Development Plan - Rutongo |  | 13524 | MP 4 |  |  |  |  | 13524
|  |  |  | 1 | Not started | TB / JK / MB | 3.5.2. Draft Community Development Plan - Nyakabingo |  | 8671 | MP 4 |  |  |  |  | 8671
|  |  |  | 1 | Not started | TB / JK / MB | 3.5.3. Draft Community Development Plan - Musha |  | 8671 | MP 4 |  |  |  |  | 8671
|  | 3.6 | Develop a performance monitoring system for the CDPs to link with UN SDG’s. | 1 | Not started | TB / MB | 3.6.1. Overall CDP M&E Plan |  | 5267 | MP 4 |  |  |  |  | 5267
|  | 3.7 | Funding model for the implementation of the CDPs through potential partnerships with government, funding agencies and the private sector. | 1 | Not started | TB / MB | 3.7.1. Budget and Funding Strategy for the CDPs |  | 4577 | MP 4 |  |  |  |  | 4577
|  | 3.8 | Stakeholder consultations and finalization of CDPs | 1 | Not started | TB / JK / MB | 3.8.1. Final Community Development Plans for all concessions |  | 21436 | MP 4 |  |  |  |  | 21436
|  | 3.9 | DFC Review and Gap Analysis | 2 | Not started | tbd | 3.9.1. DFC Review and Gap Analysis Report |  | 30000 | MP 5 | [5 empty] | 30000
|  | 3.1 | Additional socioeconomic studies | 2 | Not started | tbd | 3.10.1. Additional socioeconomic studies |  | 438664 | MP 6 | [6 empty] | 438664
|  | 3.11 | CDP implementation planning and partnerships for key projects. | 2 | Not started | TB / JK / MB | 3.11.1. CDP Project Plans |  | 64300 | MP 6 | [6 empty] | 64300
| Trinity Metals - Cost Share (TA3) | 25% of Project budget : CLO salaries, Casual staff salaries | [5 empty] | 200000
|  | Purchase of Satellite Imagery, elevation data and lidar survey's | [5 empty] | 50000
|  | Taxes WHT and VAT (28% of TB consultant fees) | [5 empty] | 27216
|  | Taxes WHT and VAT (28% of MB consultant fees) | [5 empty] | 18480
[7 empty] | Corps Africa Volunteers | 45000
|  | SRA review of land acquisiiton processes and requirements and alignment to PS5. | [5 empty] | 88165
[7 empty] | Construction of ECD Centre in Nyakabingo | 55000
|  | ECDC Support in Nyakabingo (Strong Families) | [5 empty] | 22000
[7 empty] | ECDC Support in Rutongo (Strong Families) | 26000
|  | Environmental Management (tree planting, terracing) | [5 empty] | 20000
|  | Other community Development and CSR costs | [5 empty] | 107500
| TOTAL FOR TA3 | [6 empty] | 659361 | 800000 | Should be $800K | 16267 | 0 | 13800 | 142623 | 94346 | 30000 | 502964
4 | The Development of a Legacy Tailings Management and River Rehabilitation Plan for Rutongo, Musha and Nyakabingo Concessions | 4.1 | Develop detailed SOW, R&R and Programme for the TM&RR project | 1 | In progress | GT / TS / ETEK | 4.1.1. Detailed SOW, R&R and Programme for the TM&RR project |  | 53017 | MOB+MP 2 | 16267 |  | 36750
|  | 4.2 | Mapping of all sources and receptors of contamination and GIS Analysis | 1 | In progress | GT | 4.2.1. Desktop mapping and Geographic Information System data derivation. |  | 24950 | MP 3 |  |  |  | 24950
|  |  |  | 1 | not started | GT | 4.2.2. Source, pathway and receptor analysis, including a review of gaps in ESIA assessments. |  | 23900 | MP 3 |  |  |  | 23900
|  |  |  | 1 | not started | GT | 4.2.3. Hydrocensus – location of community water sources (springs) and nature of utilisation. |  | 10550 | MP 3 |  |  |  | 10550
|  |  |  | 1 | not started | AB | 4.2.4. Geochem Assessment (waste materials and sediments) |  | 65000 | MP 3 |  |  |  | 65000
|  | 4.3 | Ecological health and drivers of the river and wetland ecosystems. | 1 | Not started | GT | 4.3.1. Determination of the PES of all the river systems |  | 49700 | MP 3 |  |  |  | 49700
|  | 4.4 | Ecosystem Goods and Services Assessments. | 1 | Not started | GT | 4.4.1. Ecosystem Goods and Services Assessment |  | 36900 | MP 4 |  |  |  |  | 36900
|  | 4.5 | Modelling catchment hydrological flows and sediment movements. | 1 | Not started | GT | 4.5.1. Catchment hydrological models |  | 65450 | MP 4 |  |  |  |  | 65450
|  | 4.6 | Determining flood lines for major streams, including climate change scenarios | 1 | Not started | GT | 4.6.1. Flood line Determination Report |  | 47200 | MP 4 |  |  |  |  | 47200
|  | 4.7 | Tailings assessment and categorization | 1 | not started | AC | 4.7.1. Tailings Resource Report |  | 80000 | MP 4 |  |  |  |  | 80000
|  | 4.8 | Review and assessment of GAP analysis of Phase 1. | 2 | Not started | tbd | 4.8.1. Gap Analysis Report |  | 19600 | MP 4 |  |  |  |  | 19600
|  | 4.9 | Additional data collection, analysis and reporting as recommended by DFC to address gaps identified in Phase 1 of this activity. | 2 | Not started | tbd | 4.9.1. Additional studies as recommended by DFC to address gaps identified in Phase 1 of this activity. |  | 78733 | MOB | 78733
|  | 4.1 | Feasibility studies for all mining concessions including comparative analyses of options for mineral recovery from legacy tailings, and remediation of waste sources and areas of contamination. | 2 | Not started | TS / GT / ETEK | 4.10.1. Legacy Tailings management and recovery feasibility study reports for each mine / mining area. |  | 105000 | MP 5 | [5 empty] | 105000
|  | 4.11 | Scenario modelling and determination of management strategies and interventions required to restore rivers and wetlands to a predetermined ecological state to maximize climate resilience | 2 | Not started | TS / GT / tbd | 4.11.1. River rehabilitation scenario modelling |  | 120000 | MP 5 | [5 empty] | 120000
|  | 4.12 | Develop Integrated Tailings Management and River Rehabilitation Plan and Programme for each Concession | 2 | Not started | TS / GT | 4.12.1. Integrated Tailings Management and River Rehabilitation Plan and Programme for each Concession |  | 170000 | MP 6 | [6 empty] | 170000
| Trinity Metals - Cost Share (TA4) | 25% of Project budget : In kind: Tech Services salaries and expenses etc | [5 empty] | 237500
|  | Consulting fees from Tailings Engineers (TAILINGS SOLUTIONS) for the design of engineered and GIIP-compliant tailings facilities | [5 empty] | 40000
|  |  | Water quality monitoring database and dashboard, incorporating existing and future data (Ground Truth) |  |  |  |  | 20515
|  | Taxes WHT and VAT (28% on SLR fees) | [5 empty] | 18200
|  | Taxes WHT and VAT (28% of GT consultant fees) | [5 empty] | 82712
|  | 28% WHT and VAT taxes on Phase 2 consulting fees | [5 empty] | 89600
|  | Physical rehabiliation work at Karambo mine | [5 empty] | 198000
|  | Masoro and Karambo Illegal Miner Integration Pilot Projects (re-mining of tailings) | [5 empty] | 20000
|  | Additional consulting fees from Mining and Resource Consultants | [5 empty] | 150000
|  | Mine Rehabilitation and closure quantification (ETEK) | [5 empty] | 178750
| TOTAL FOR TA4 | [6 empty] | 1035277 | 950000 | Should be 950K | 95000 | 0 | 36750 | 174100 | 249150 | 225000 | 170000
5 | Preliminary Assessment/Site Inspections for all three of the TMG mines (Rutongo, Nyakabingo and Musha) | 5.1 | Preliminary Assessment/Site Inspections for an estimated 9 separate mine sites in three mining concessions (7 separate sites at the Rutongo concession), including the following components: a. Characterization of mine waste sources, ambient air, soil, groundwater surface water and sediment b. Analysis of hydrogeology; identification of ecological and human receptors with an analysis of potential impacts to these receptors from existing contamination and contaminant migration. | 1 | In progress | SLR | 5.1.1. SLR Inception Report |  | 30000 | MP 1 |  | 30000
|  |  |  | 1 | In progress | SLR | 5.1.2. SLR Nyakabingo Feasibility Study and Gap Analysis Report |  | 30000 | MP 1 |  | 30000
|  |  |  | 1 | In progress | SLR | 5.1.3. Baseline studies: 1. Geohydrology (report and modelling) 2. Hydrology (report, water balances and stormwater management plans) 3. Cultural Heritage 4. Air Quality. 5. Noise 6. Climate Change Assessment 7. Human Rights Assessment 8. Social Impact Assessment 9. Geochem assessment 10. Aquatic Biodiversity |  | 200000 | MP 1 |  | 200000
|  |  |  | 1 | In progress | SLR | 5.1.4. Environmental and Social Impact Assessment Reports (Rutongo and Musha) |  | 97000 | MP 2 |  |  | 97000
|  |  |  | 1 | In progress | SLR | 5.1.5. Environmental and Social Management Plans (Rutongo and Musha) |  | 101500 | MOB | 101500
|  |  |  | 1 | In progress | SLR | 5.1.6. ESIA and SEMP - Nyakabingo Mine |  | 50000 | MP 2 |  |  | 50000
|  | 5.2 | Review and assessment of GAP analysis of Phase 1. | 2 | Not started |  | 5.2.1. Review, Gap Analysis, and SOW for additional studies |  | 40000 | MP 3 |  |  |  | 40000
|  | 5.3 | Additional data collection, analysis and reporting as recommended by DFC to address gaps identified in Phase I of this task. | 2 | Not started | tbc | 5.3.1. Additional Baseline Studies as defined by Gap Analysis |  | 466500 | MP 5 | [5 empty] | 200000 | 266500
| Trinity Metals - Cost Share (TA5) | 25% of the Project Budget: E&S Staff salaries, transport, expenses etc) | [5 empty] | 250000
|  | Taxes WHT and VAT(28% of SLR consulting fees) | [5 empty] | 192387
|  | Taxes WHT and VAT (28% of additional studies undertake as part of Phase 2 | [5 empty] | 140000
|  |  |  | Trinity cost-share of ESIA (SLR May-June 2024 invoices) |  |  |  | 261666
|  | Drillings of boreholes (Africa Drilling) | [5 empty] | 125271
|  | Additional Geohydrology consulting fees and dewatering boreholes (MvB) | [5 empty] | 65000
|  | Water, Air quality, noise monitoring and reporting (18 months) | [5 empty] | 40000
|  | Dam 4 construction and Stormwater Management Structure construction- Nyakabingo | [5 empty] | 383061
|  |  | ETS engineering fees for dam and storm water management |  |  |  |  | 108939
|  | 28% WHT and VAT on ETS design work (above) | [5 empty] | 30503
| TOTAL FOR TA5 | [6 empty] | 1596827 | 1015000 | Should be 1,015K | 101500 | 260000 | 147000 | 40000 | 0 | 200000 | 266500
GRAND TOTAL | [7 empty] | 5436735.91 | 3865000 | Should be $3,865,000 | 388767 | 452000 | 337550 | 551723 | 553496 | 642000 | 939464
[7 empty] | Should be | 3865000 | 3865000 |  | 386500 | 452000 | 337550 | 551723 | 573496 | 642000 | 921731
[7 empty] | DIFFERENCE | 1571735.91 | 0 |  | 2267 | 0 | 0 | 0 | -20000 | 0 | 17733
0
2030000
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 28% of both SML4 Change contracts
Note on K24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Switched this from MOB to MP4
Note on P24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Push to 2026
Note on I34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimate based on budget
Note on L40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remainder of Jo’s invoices /2
Note on I58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/2 of 28% of 22 months as per contract
Note on G72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might have SLR support this
Note on J97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These should reflect actual costs so we can add the difference between the MPs to the Mobilization payment (not cost share - except for what was already reported as cost-share in MP1)
Note on L97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Variation Order + remainder of SLR invoices to date
Note on C107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where is this budgeted for? Reply: There is budget in the mines OPs budget
Note on L115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to reduce an activity’s MOB by this amount...

## Revised Budget 2.0
[12 empty] | 2024-06-01 | 2024-08-01 | 2025-01-01 | 2025-04-01 | 2025-11-28 | 2026-02-01 | 2026-05-01 | 2026-09-01
# | Activity | # | Tasks | Phase | Status | Service Provider | Deliverables | Original TMG Co-Spend | Revised TMG Co-spend | TA Budget | Milestone Payment No. | Mobilization Payment Jun 24 | MP 1 Aug 24 | MP 2 Jan 25 | MP2 Add Apr 25 | MP 3 Oct 25 | MP 4 Feb 26 | MP 5 May 26 | MP 6 Sep 26 | Actual Co-Spend | Actual DFC Spend | % completion DFC Quarterly Meeting
1 | Trinity Metals Group Skills Training and People Development | 1.1 | Full Training Needs Assessment and Analysis across the Trinity Group. | 1 | Completed | SML4 Change | 1.1.1. Organisational Training needs assessment & analysis : Report |  |  | 16000 | MP 1 | 2024-08-01: 16000 |  | 16000
|  |  |  | 1 | Completed | SML4 Change | 1.1.2. Organisational Training needs assessment and Analysis: Plan |  |  | 16000 | MP 1 | 2024-08-01: 16000 |  | 16000
|  | 1.2 | Development and delivery of phase 1 training programs - leadership program for all Supervisors and Managers, competency-based training, blasting certificate program, formal training function (ToT), etc. | 1 | Completed | SML4 Change | 1.2.1. Monthly progress reports and supporting documentation for the delivery of phase 1 training programs (Part A) | 137600 | 137600 | 80000 | MP 1 | 2024-08-01: 80000 | 137600 | 80000
|  |  |  | 1 | Completed | SML4 Change | 1.2.2. Monthly progress reports and supporting documentation for delivery of phase 1 training programs (Part B) | 20487 | 20487 | 209327 | MOB, MP 2 | 2024-06-01: 109327; 2025-01-01: 100000 | 20487 | 209327
|  | 1.3 | Development and implementation of phase 2 training programs focused on Coaching and Mentoring, Compliance, Safety, etc. and continuation of some phase 1 training programs (technical training, formal training structure, leadership training, etc) | 2 | Completed | SML4 Change | 1.3.1. Monthly progress reports and supporting documentation for phase 2 training programs (Part A) |  |  | 189699.19 | MP 2 Add | 2025-04-01: 189699.19 |  | 188289.79
|  |  |  | 2 | not started | SML4 Change | 1.3.2. Monthly progress reports and supporting documentation for phase 2 training programs (Part B) |  |  | 92000 | MP 3 | 2025-11-28: 77947.94 |  | 14052.06
|  |  |  | 2 | not started | SML4 Change | 1.3.3. Monthly progress reports and supporting documentation for phase 2 training programs (Part C) |  |  | 67000 | MP 4 | 2026-02-01: 77000
|  | 1.4 | Development and implementation of E-learning Platform | 2 | not started | SML4 Change | 1.4.1. E-learning platform |  |  | 29974 | MP 4 | 2026-02-01: 34026
| Trinity Metals - Cost Share | 25% of Project budget : Internal Trinity HR training staff salaries, accommodation and transportation of trainees | [5 empty] | 175000
|  |  | Taxes WHT and VAT (28% of external consultant fees) |  |  |  |  | 194409 | 174720 | [10 empty] | 105340
|  | Additional Costs for SML consultants (Flights, transport and accommodation etc) | [5 empty] | 60000 | 60000 | [10 empty] | 45450
[7 empty] | Training meals and drinks | 100000 | 75000 | [10 empty] | 60497
Overseas and in-country training sponsorships of Trinity staff
[7 empty] | First responder training (paramedics) | 60000
|  | Trinity-funded 2025 Training | [5 empty] | 215093
|  | Trinity-funded 2026 Training | [5 empty] | 90268
| TOTAL FOR A1 | [6 empty] | 1052857 | 467807 | 700000.19 | should be 700K | 109327 | 112000 | 100000 | 189699.19 | 77947.94 | 111026 | 0 | 0 | 369374 | 523668.85 | 100%
2 | Development and Implementation of an integrated, group-wide SHEC Management System. | 2.1 | Gap Analysis. Review of all SHEC system procedures, registers and records, identification of gaps and design program for SHEC system development and implementation. | 1 | Completed | GF & JLD | 2.1.1. Gap analysis, plan and programme for implementation of the SHEC MS | 41933.4 | 41933.4 | 30000 | MP 1 | 2024-08-01: 30000 | 41933.4 | 30000
|  | 2.2 | Baseline-Risk Assessment and Impact/Aspect Register for all operations and activities, undertaking the necessary training of SHEC and operational staff. | 1 | Completed | GF & JLD | 2.2.1. Baseline Risk Assessment for all activities across the entire TMG group. (MP 1) | 23888.87 | 23888.87 | 15000 | MP 1 | 2024-08-01: 15000 | 23888.59 | 15000
|  |  |  | 1 | Completed | GF & JLD | 2.2.2. Training of SHEC staff and supervisors in BLRA procedure. |  |  | 10000 | MP 2 | 2025-01-01: 10000 |  | 10000
|  |  |  | 1 | In progress | GF & JLD | 2.2.3. Impact/Aspect Register for Group and for each of the Mines |  |  | 31200 | MP 2Add | 2025-04-01: 31200 |  | 28879.3
|  | 2.3 | Geotechnical engineering/structural analyses for underground workings and tailings/waste piles and dams. | 1 | Completed | OHMS / ETS | 2.3.1. Geotechnical/Engineering Structure Reports for all the mines |  |  | 20000 | MP 1 | 2024-08-01: 20000 |  | 20000
|  |  |  | 1 | In progress | OHMS / ETS | 2.3.2. Additional quarterly geotechnical/engineering structure reports for all the mines |  |  | 64865 | MP 2-5 |  |  | 25000 | 7865 | 10090.91 | 8000 | 8000 | 8000 |  | 32865
|  | 2.4 | Baseline OH Surveys for all OH risk-exposure working areas (include: vibration, noise, ventiliation, dust, light and ergonomic, gasses etc) | 1 | Q1 2025 | tbc | 2.4.1. OHS Baseline Survey results and recommendations |  |  | 40000 | MP4 | 2026-05-01: 40000
|  | 2.5 | Setting of the SHEC Targets and Objectives at a corporate level and across all mining operations | 2 | Completed for Trinity for 2024 | GF & JLD | 2.5.1. SHEC targets and objectives for 2024 (completed) | 3184 | 1946.48 | 5000 | MP 1 | 2024-08-01: 5000 | 1946.48 | 5000
|  |  |  | 2 | Completed | GF & JLD | 2.5.2. SHEC Targets and objectives for 2025. |  |  | 5584 | MP 2 | 2025-01-01: 5584 |  | 5584
|  | 2.6 | SHEC System procedure development, covering all elements related to ISO 14001: 2015 and ISO 45001: 2018. | 2 | In progress | GF & JLD | 2.6.1. All SHEC System Procedures developed. |  |  | 30000 | MP 2Add | 2025-04-01: 30000 |  | 30000
|  | 2.7 | Operational Environmental and Social Action Plan (ESAP), aligned to the ESIA, Impact Aspect register, legal register and lender requirements. | 2 | Completed | GF & JLD | 2.7.1. Highlevel TMG ESAP (completed and updated regularly. |  |  | 10000 | MP 1 | 2024-08-01: 10000 |  | 10000
|  |  |  | 2 | In progress (Nyakabingo completed) | GF & JLD | 2.7.2. ESAPs for each of the Mines. |  |  | 16000 | MP 3 | 2025-11-28: 17355.39 |  | 9508.52
|  | 2.8 | Implementation of the SHEC System Procedures. | 2 | In progress | GF & JLD | 2.8.1. Internal audit report on SHEC management system implementation |  |  | 16000 | MP 4 | 2026-02-01: 12554
|  | 2.9 | Training and Mentoring of management and SHEC personnel in the MS implementation. | 2 | In progress | JLD & tbc | 2.9.1. External audit report on SHEC management system implementation |  |  | 40000 | MP 6 | 2026-09-01: 40000
|  | 2.1 | Behavior Based Care (BBC) System development and implementation | 2 | not started | tbc | 2.10.1. Behavior Based Care (BBC) System development and implementation |  |  | 66351 | MP 6 | 2026-09-01: 66351
| Trinity Metals - Cost Share (B) | 25% of Project Budget: Gerrit's salary, HSE Staff salaries, and First Responder salaries | [5 empty] | 75000
[7 empty] | Taxes WHT and VAT (28% of JLD and OHMS) | 100000 | 100000 | [10 empty] | 54706.07
|  | Purchase Ambulances for each of the mines | [5 empty] | 214000 | 213910.38 | [10 empty] | 213910.38
|  | Purchase of INX in control | [5 empty] | 40000 | 41354 | [10 empty] | 41354
[6 empty] | Void Fill to stabilize ground conditions in tunnels |  | 122000 | 122000 | [10 empty] | 122000
[7 empty] | Ground water test kits | 870.59 | 870.59 | [10 empty] | 870.59
[7 empty] | Safety Training Materials | 7230.44 | 7230.44 | [10 empty] | 7230.44
Gas detectors, training and callibration
|  | Medical Surveillance Programme | [5 empty] | 183000
|  | PPE Provision | [5 empty] | 547346 | 547346 | [10 empty] | 432904.01
| TOTAL FOR B | [6 empty] | 1358453.3 | 1100480.16 | 400000 | Should be 400K | 0 | 80000 | 40584 | 69065 | 27446.3 | 20554 | 48000 | 114351 | 940743.96 | 196836.82 | 59.41%
3 | Formulation of the Community Development Plans (CDPs) for the Concessions. | 3.1 | Develop detailed SOW, R&R and Programme for the CDPs | 1 | Completed | TB / JK/ MB | 3.1.1. Detailed SOW, R&R and Programme for the CDPs | 1115 | 1115 | 15600 | MP 2 | 2025-01-01: 15600 | 1115 | 15600
|  |  |  | 1 | Completed | TB / JK/ MB | 3.1.2. CDP Inception Report |  |  | 15000 | MP 3 | 2025-11-28: 18000
|  | 3.2 | Development of a Stakeholder Database and Engagement Plan | 1 | In Progess | TB / JK/ MB / CA | 3.2.1. Stakeholder Database and Engagement Plan |  |  | 35000 | MP 3 | 2025-11-28: 35456.15 |  | 5700
|  | 3.3 | Baseline review and analysis for all three concessions, including land use mapping | 1 | Not started | TB / JK / MB | 3.3.1. Draft Status Quo Reports |  |  | 25000 | MP 3 | 2025-11-28: 26250
|  |  |  | 1 | In Progess | Ganza Green/Light Image | 3.3.2.Draft landuse maps (GIS mapping, lidar surveys, satellite imagery, elevation data, etc) |  |  | 30000 | MP 4 | 2026-02-01: 30000
|  |  |  | 1 | In Progess | Ganza Green/Light Image | 3.3.3. Detailed landuse maps for each of the concessions (GIS mapping, lidar surveys, satellite imagery, elevation data, etc) |  |  | 84294 | MP 4 | 2026-02-01: 84294
|  |  |  | 1 | Completed | TB / JK / MB | 3.3.4. Final Status Quo Reports |  |  | 20000 | MP 4 | 2026-02-01: 20000
|  | 3.4 | Needs analysis and livelihood assessment for each of the concessions | 1 | In Progress | TB / JK / MB / CA | 3.4.1. Concession Community Needs Analysis and Livelihoods Assessment Reports |  |  | 50000 | MP 4 | 2026-02-01: 50000
|  | 3.5 | Drafting of the Community Development Plans for each concession | 1 | Not started | TB / JK / MB / CA | 3.5.1. Draft Community Development Plan - Rutongo |  |  | 40000 | MP 5 | 2026-05-01: 40000
|  |  |  | 1 | Not started | TB / JK / MB | 3.5.2. Draft Community Development Plan - Nyakabingo |  |  | 20000 | MP 5 | 2026-05-01: 20000
|  |  |  | 1 | Not started | TB / JK / MB | 3.5.3. Draft Community Development Plan - Musha |  |  | 20000 | MP 5 | 2026-05-01: 20000
|  | 3.6 | Develop a performance monitoring system for the CDPs to link with UN SDG’s. | 1 | Not started | TB / MB | 3.6.1. Overall CDP M&E Plan |  |  | 15000 | MP 5 | 2026-05-01: 15000
|  | 3.7 | Funding model for the implementation of the CDPs through potential partnerships with government, funding agencies and the private sector. | 1 | Not started | TB / MB | 3.7.1. Budget and Funding Strategy for the CDPs |  |  | 15000 | MP 5 | 2026-05-01: 15000
|  | 3.8 | Stakeholder consultations and finalization of CDPs | 1 | Not started | TB / JK / MB / CA | 3.8.1. Final Community Development Plans for all concessions |  |  | 30000 | MP 6 | 2026-09-01: 30000
|  | 3.9 | DFC Review and Gap Analysis | 2 | Not started | TB/ JLD / MB | 3.9.1. DFC Review and Gap Analysis Report |  |  | 30000 | MP 5 | 2026-05-01: 30000
|  | 3.1 | Additional socioeconomic studies | 2 | Not started | tbd | 3.10.1. Additional socioeconomic studies |  |  | 190106 | MP 6 | 2026-09-01: 185400
|  | 3.11 | CDP (LED) implementation planning and partnerships for key projects. | 2 | Not started | TB / JK / MB / CA | 3.11.1. CDP (LED) Project Plans |  |  | 65000 | MP 6 | 2026-09-01: 65000
|  |  |  | 2 | Not started | PCV / CA | 3.11.2 CDP (LED) Pilot projects |  |  | 100000 | MP 6 | 2026-09-01: 100000
| Trinity Metals - Cost Share (TA3) | In-kind: 25% of Project budget : CLO salaries, Casual staff salaries | [5 empty] | 200000
|  | Purchase of Satellite Imagery, elevation data and lidar survey's | [5 empty] | 50000
|  | Taxes WHT and VAT (28% of consultant fees) | [5 empty] | 45696 | 45696 | [10 empty] | 1864.12
[6 empty] | Techmet Support of Corps Africa Volunteers |  | 30000 | 30000 | [10 empty] | 30000
|  | Techmet support of SRA review of land acquisiiton processes and requirements and alignment to PS5 | [5 empty] | 88165 | 79792.83 | [10 empty] | 79792.83
[6 empty] | Techmet support of Construction of ECD Centre in Nyakabingo |  | 55000 | 55000
|  | Techmet support of ECDC Management in Nyakabingo (Strong Families) | [5 empty] | 10000 | 10000
[7 empty] | ECDC Management in Rutongo (Strong Families) | 26000 | 24000 | [10 empty] | 14711.953
|  | Environmental Management (tree planting, terracing) | [5 empty] | 20000
[6 empty] | Martina Bennett TA grant management support |  | 17400 | 17400 | [10 empty] | 47225
|  | Other community Development and CSR costs | [5 empty] | 107500 | 20000
[7 empty] | Nyakabingo bus station | 222000
[7 empty] | TOTAL FOR TA3 | 650876 | 283003.83 | 800000 | Should be $800K | 0 | 0 | 15600 | 0 | 79706.15 | 184294 | 140000 | 380400 | 174708.903 | 21300 | 34.95%
4 | The Development of a Legacy Tailings Management and River Rehabilitation Plan for Rutongo, Musha and Nyakabingo Concessions | 4.1 | Develop detailed SOW, R&R and Programme for the TM&RR project | 1 | Completed | GT / TS / ETEK | 4.1.1. Detailed SOW, R&R and Programme for the TM&RR project | 2295.13 | 2295.13 | 36920 | MP 2 | 2025-01-01: 36920 | 2295.13 | 36920
|  | 4.2 | Mapping of all sources and receptors of contamination and GIS Analysis | 1 | In progress | GT | 4.2.1. Desktop mapping and Geographic Information System data derivation. |  |  | 24950 | MP 5 | 2026-05-01: 24950
|  |  |  | 1 | not started | GT | 4.2.2. Source, pathway and receptor analysis, including a review of gaps in ESIA assessments. |  |  | 23900 | MP 4 | 2026-02-01: 23900
|  |  |  | 1 | not started | GT | 4.2.3. Hydrocensus – location of community water sources (springs) and nature of utilisation. |  |  | 28149.62 | MP 3 | 2025-11-28: 28149.62
|  |  |  | 1 | completed | AB | 4.2.4. Geochem Assessment (waste materials and sediments) - Field Work Report |  |  | 32568 | MP 3 | 2025-11-28: 32568
|  |  |  | 1 | not started | AB | 4.2.5. Geochem Assessment (waste materials and sediments) - Final Report |  |  | 35866 | MP 4 | 2026-02-01: 35866
|  | 4.3 | Ecological health and drivers of the river and wetland ecosystems. | 1 | Not started | GT | 4.3.1. Determination of the PES of all the river systems - Field Work Report |  |  | 24850 | MP 4 | 2026-02-01: 24850
[5 empty] | Not started | GT | 4.3.2. Determination of the PES of all the river systems - Final Technical Report |  |  | 24850 | MP 5 | 2026-05-01: 24850
|  | 4.4 | Ecosystem Goods and Services Assessments. | 1 | Not started | GT | 4.4.1. Ecosystem Goods and Services Assessment |  |  | 36900 | MP 5 | 2026-05-01: 36900
|  | 4.5 | Modelling catchment hydrological flows and sediment movements. | 1 | Not started | GT | 4.5.1. Catchment hydrological models - Field Work Report |  |  | 34624.24 | MP 3 | 2025-11-28: 34624.24
[5 empty] | Not started | GT | 4.5.2. Catchment hydrological models - Final Technical Report |  |  | 32725 | MP 5 | 2026-05-01: 32725
|  | 4.6 | Determining flood lines for major streams, including climate change scenarios | 1 | Not started | GT | 4.6.1. Flood line Determination Fieldwork Report |  |  | 25499.24 | MP 3 | 2025-11-28: 25499.24
[5 empty] | Not started | GT | 4.6.2. Flood line Determination Final Technical Report |  |  | 23600 | MP 5 | 2026-05-01: 23600
|  | 4.7 | Tailings assessment and categorization | 1 | not started | tbc | 4.7.1. Tailings Resource Report |  |  | 80000 | MP 4 | 2026-05-01: 80000
|  | 4.8 | Reviewing water quality monitoring protocols including the development of an online water quality monitoring database and dashboard. | 1 | not started | GT | 4.8.1. Water quality monitoring database and dashboard, incorporating existing and future data |  |  | 18650 | MP 4 | 2026-02-01: 18650; 2026-05-01: 18650
|  | 4.9 | Review and assessment of GAP analysis of Phase 1. | 2 | Not started | JLD | 4.9.1. Gap Analysis Report |  |  | 19600 | MP 5 | 2026-05-01: 19600
|  | 4.1 | Additional data collection, analysis and reporting as recommended by DFC to address gaps identified in Phase 1 of this activity. | 2 | Not started | tbd | 4.10.1. Additional studies as recommended by DFC to address gaps identified in Phase 1 of this activity. |  |  | 95000 | MP 5 | 2026-05-01: 95000
|  | 4.11 | Feasibility studies for all mining concessions including comparative analyses of options for mineral recovery from legacy tailings, and remediation of waste sources and areas of contamination. | 2 | Not started | ETS / GT / ETEK | 4.11.1. Legacy Tailings management and recovery feasibility study reports for each mine / mining area. |  |  | 71348 | MP 6 | 2026-09-01: 71348
|  | 4.12 | Scenario modelling and determination of management strategies and interventions required to restore rivers and wetlands to a predetermined ecological state to maximize climate resilience | 2 | Not started | ETS / GT / tbd | 4.12.1. River rehabilitation scenario modelling |  |  | 80000 | MP 6 | 2026-09-01: 80000
|  | 4.13 | Develop Integrated Tailings Management and River Rehabilitation Plan and Programme for each Concession | 2 | Not started | ETS / GT | 4.13.1. Integrated Tailings Management and River Rehabilitation Plan and Programme for each Concession |  |  | 80000 | MP 6 | 2026-09-01: 80000
|  | 4.14 | Pilot project on legacy tailings and river rehabilitation | 2 | not started | JLD / GT / PCV | 4.14.1. Project plan and designs for pilot project on legacy tailings and river rehab |  |  | 40000 | MP 5 | 2026-05-01: 40000
|  |  |  | 2 | not started | JLD / GT / PCV | 4.14.2. Report on pilot project on legacy tailings and river rehab |  |  | 80000 | MP 6 | 2026-09-01: 80000
| Trinity Metals - Cost Share (TA4) | 25% of Project budget : In kind: Geologists, Geotech Engineers salaries | [5 empty] | 237500
|  | Consulting fees from Tailings Engineers (TAILINGS SOLUTIONS) for the conceptual designs of engineered and GIIP-compliant tailings facilities | [5 empty] | 204834.46 | 204834.46 | [10 empty] | 204834.46
|  | Taxes WHT and VAT (28% on TA4 consultant fees) | [5 empty] | 190512 | 190512 | [10 empty] | 125653.61
|  | Physical rehabiliation work at Karambo mine (Rutongo Mine) | [5 empty] | 198000
|  | Additional consulting fees from Mining and Resource Consultants (Bara & GB) | [5 empty] | 89448 | 89448 | [10 empty] | 89447.54
| TOTAL FOR TA4 | [6 empty] | 922589.59 | 487089.59 | 950000.1 | Should be 950K | 0 | 0 | 36920 | 0 | 120841.1 | 103266 | 396275 | 311348 | 422230.74 | 36920 | 27.48%
5 | Preliminary Assessment/Site Inspections for all three of the TMG mines (Rutongo, Nyakabingo and Musha) | 5.1 | Preliminary Assessment/Site Inspections for an estimated 9 separate mine sites in three mining concessions (7 separate sites at the Rutongo concession), including the following components: a. Characterization of mine waste sources, ambient air, soil, groundwater surface water and sediment b. Analysis of hydrogeology; identification of ecological and human receptors with an analysis of potential impacts to these receptors from existing contamination and contaminant migration. | 1 | Completed | SLR | 5.1.1. SLR Inception Report |  |  | 30000 | MP 1 | 2024-08-01: 30000 |  | 30000
|  |  |  | 1 | Completed | SLR | 5.1.2. SLR Nyakabingo Feasibility Study and Gap Analysis Report |  |  | 30000 | MP 1 | 2024-08-01: 30000 |  | 30000
|  |  |  | 1 | Completed | SLR | 5.1.3. Baseline studies: 1. Geohydrology (report and modelling) 2. Hydrology (report, water balances and stormwater management plans) 3. Cultural Heritage 4. Air Quality. 5. Noise 6. Climate Change Assessment 7. Human Rights Assessment 8. Social Impact Assessment 9. Geochem assessment 10. Aquatic Biodiversity | 18950 | 18950 | 317926.35 | MP 1 & MOB | 2024-06-01: 117926.1; 2024-08-01: 200000.25 | 18950 | 317926.35
|  |  |  | 1 | Completed | SLR | 5.1.4. Environmental and Social Impact Assessment Reports (Rutongo and Musha) | 6056.1 | 6056.1 | 100843.75 | MP 2 | 2025-01-01: 100843.75 | 6056.1 | 100843.75
|  |  |  | 1 | Completed | SLR | 5.1.5. Environmental and Social Management Plans (Rutongo and Musha) |  |  | 90482 | MOB | 2024-06-01: 90482 |  | 90482
|  |  |  | 1 | Completed | SLR | 5.1.6. ESIA and ESMP - Nyakabingo Mine |  |  | 118764.5 | MP 2 & MOB | 2024-06-01: 68764.5; 2025-01-01: 50000 |  | 118764.5
|  |  |  | 1 | In progress | SLR | 5.1.7. Revised Final ESIAs in response to comments |  |  | 6052 | MP 3 | 2026-02-01: 6052
|  | 5.2 | Mine rehabilitation and closure quantification | 1 | In progress | ETEK | 5.2.1. Mine Rehabilitation and closure quantification report for each mine |  |  | 95334.82 | MP 3 | 2025-11-28: 95334.82 |  | 37737.94
|  | 5.3 | Long-term surface and ground water monitoring | 1&2 | In progress | Talbot | 5.3.1. Monthly water monitoring result reports |  |  | 45000 | MP 3,4&5 | 2025-11-28: 18792.38; 2026-02-01: 12000; 2026-05-01: 14208
|  | 5.3 | Review and assessment of GAP analysis of Phase 1. | 2 | Not started | JD | 5.2.1. Review, Gap Analysis, and SOW for additional studies |  |  | 40000 | MP 3&4 | 2025-11-28: 22836.77; 2026-02-01: 17163
|  | 5.4 | Additional data collection, analysis and reporting as recommended by DFC to address gaps identified in Phase I of this task. | 2 | Not started | tbc | 5.3.1. Additional specialist reports to address gaps |  |  | 140597 | MP 5 & MP 6 | 2026-05-01: 70298.5; 2026-09-01: 70298.5
| Trinity Metals - Cost Share (TA5) | 25% of the Project Budget: E&S Staff salaries | [5 empty] | 250000
|  | Taxes WHT and VAT(28% of TA5 consulting fees) | [5 empty] | 332387 | 106575 | [10 empty] | 106575.29
|  | Drillings of boreholes (Africa Drilling) | [5 empty] | 125271 | 125271 | [10 empty] | 125271
|  | Additional Geohydrology consulting fees and dewatering boreholes (MvB) | [5 empty] | 65000 | 6615 | [10 empty] | 6615
|  | Water, Air quality, noise monitoring and reporting (18 months) (Talbot) | [5 empty] | 40000
|  | Dam 4 construction and Stormwater Management Structure construction- Nyakabingo | [5 empty] | 389180.9 | 389180.9 | [10 empty] | 389180.9
|  |  | ETS engineering fees for dam and storm water management |  |  |  |  | 139223.53 | 139223.53 | [10 empty] | 139223.53
[7 empty] | Water treatment plant construction | 45000 | 45000
|  | Annual large data room subscription | [5 empty] | 31553.06 | 15777 | [10 empty] | 15776.53
| TOTAL FOR TA5 | [6 empty] | 1442621.59 | 852648.53 | 1015000.42 | Should be 1,015K | 277172.6 | 260000.25 | 150843.75 | 0 | 136963.97 | 35215 | 84506.5 | 70298.5 | 807648.35 | 725754.54 | 84.75%
[7 empty] | In kind contributions: Salaries of Trinity employees who support the implementation of TA activities (max 25% of TA budget) | 966250.1775 | 966250.1775
GRAND TOTAL | [7 empty] | 6393647.6575 | 4157279.2875 | 3865000.71 | Should be $3,865,000 | 386499.6 | 452000.25 | 343947.75 | 258764.19 | 442905.46 | 454355 | 668781.5 | 876397.5 | 2714705.953 | 1504480.21
[7 empty] | Should be | 3865000 | 3865000 | 3865000 |  | 386500 | 452000 | 337550 |  | 551723 | 573496 | 642000 | 921731
[7 empty] | DIFFERENCE | -2528647.6575 | -292279.2875 | 0.71 |  | -0.4 | 0.25 | 6397.75 |  | -108817.54 | -119141 | 26781.5 | -45333.5
0.70238
2030000.84
[13 empty] | 3865000 | 3883651.25
Need salary amounts for June 2024-Sept 2026 for:
Sam
Gerrit
SHEC Superintendents and Officers
Geotech Engineers
Geologists (partial)
MRM staff (partial)
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Some of this could possibly go into the DFC TA budget if the TA1 budget is increased. However, some of the invoices that were claimed as cost share are a bit old (Q4 2023, Q1 2024) and I’m not sure they would agree to that...
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This could potentially go into the DFC TA budget, if the TA1 budget is increased...
Note on V7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to reconcile this in next MP3 request
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per cash forecast
Note on Q8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated SML invoice for Q3 2025 (to be paid in Oct 2025)
Note on K9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated SML Q4 2025 invoice if LOE is not reduced
Note on R9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated SML invoice for Q4 2025
Note on K10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We will still have one more quarter to cover from SML’s contract, the invoice for which would be submitted in the MP5 request. Does this amount and deliverable match up?
Note on R10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Possible that this will be pushed to MP5
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there internal training staff? Reply: To discuss with David
Note on J11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved this amount to TA2 instead.
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 28% of both SML4 Change contracts
Note on V23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to reconcile this in next MP3 request
Note on J24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is this cost share from? We’ve claimed all of OHMS invoices…
Note on P25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This was originally budgetd at 25K, but OHMS invoice submitted with MP2Add was only $7865
Note on L26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Switched this from MOB to MP4
Note on R26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: potential shift to MP 5
Note on J27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to reconcile this in next cost share report.
Note on U27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jo’s travel
Note on K31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Increase budget? We will have $33k in Jo’s invoices to cover by Oct 2025 (MP3)
Note on K32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Increase budget?
Note on R32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: allocate JD invoices between Nov and Jan Reply: need final copies of the final audit report
Note on L33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Push to MP 6
Note on L34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Push to MP 6
Note on R34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check w/ GF on potential spend for BBC, internal or external? SML4 Change to shift to TA2 trainings or shift funds to TA 1
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think we should take out transportation costs from this, but could we justify all of Gerrit’s salary as in-kind? And what about all of the HSE staff? First responder salaries? Etc?
Note on H42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check with GF if there is an updated budget or spend for this activity and medical surv. program
Note on U46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tony’s travel
Note on Q47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Martina’s fees
Note on Q48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tony will have only $22k in invoices by Oct25. I will have $18k for Jun-Aug-Sep, but not sure all of that could be claimed for this deliverable… Justus will have $3200 in invoices Reply: Tony invoices plus Govern Well
Note on Q49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The rest of the deliverables under MP3 should be shifted to later. Reply: Corps Africa
Note on R51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LiDAR and Ganza Green to be claimed here Reply: 40% up front for LiDAR, balance likely due at end of Feb. Ganza Green partial invoice by end of Feb
Note on R52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TB claimed $6,110, (Nov/Dec), ABH invoice, GovernWell
Note on R53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WorldVision, ABH, TB,
Note on H54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include another deliverable all the stakeholder engagement activities (launch agenda and minutes from meetings)
Note on C64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check CLO salaries and actual titles/salaries of tree planters
Note on I66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/2 of 28% of 22 months as per contract Reply: I merged TB and MB taxes into one line for TA3 consultant taxes
Note on J66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/2 of 28% of 22 months as per contract Reply: I merged TB and MB taxes into one line for TA3 consultant taxes
Note on H71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check with Sam on how much this is
Note on C72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check with Sam on costs associated with this
Note on C74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How much are the cows and bus terminal costs?
Note on J74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bus station = 222K
Note on I77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jo’s travel
Note on J77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jo’s travel
Note on L78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be done by 31 Mar 2026
Note on K80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was 10,550 in the previous budget for some reason...
Note on L82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due on 31 Oct 2025, but won’t be paid until Nov 25
Note on R82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: invoices mostly paid
Note on K83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Split these into two deliverables
Note on L83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due Dec 2025
Note on K84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add Jo’s invoices in to this budget
Note on L84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due 31 Mar 2026
Note on L85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due 31 Mar 2026
Note on K86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Split these into two deliverables
Note on L86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due Aug 2025
Note on L87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due 31 Mar 2026
Note on L88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due Aug 2025
Note on L89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Now due 31 Mar 2026
Note on R90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: shifted to an internal project, potential reallocation to another activity - under TA 1
Note on S90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: shifted from MP4, potential internal allocation
Note on S91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On track for MP 4 invoicing
Note on J99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved 100k from TA3. Could be more than this - need to get actual amounts.
Note on C102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Started under priority project, need to track
Note on I103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check on cost share vs. DFC claim
Note on J108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Additional fees for ESIAs (Courrier sample, sattelite imagery)
Note on R112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need SLR invoicing
Note on Q113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ETEK fees and travel and ½ Jo’s fees
Note on V113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to reconcile this in MP3 request and next cost-share report
Note on R114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: expect invoices - check with Benon
Note on Q115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ½ Jos Fees plus Martina’s fees
Note on R115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check JD invoices
Note on S116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential shift - keep for potential due diligence
Note on C117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which staff could we put towards this one, that aren’t already accounted for above? Sam? But it would be only a portion of his salary and that’s where it becomes tricky. Perhaps we remove from here.