Project: Internet Connectivity Optimization – Trinity Metals Sites

1. Background & Objective

Trinity Metals intends to enhance network reliability, performance, and cost efficiency across all mine sites (Nyakabingo, Rutongo, Musha) by:

- Introducing Starlink (Hyperlink Networks) as the Primary Internet Link

- Retaining MTN Rwanda as Backup Connectivity

- Optimizing bandwidth consumption and cost

This change aligns with the company’s digital transformation and uptime requirements.

2. Current Situation (As-Is)

Based on existing MTN agreements:

- MTN provides:

  - Broadband Internet

  - VPN Connectivity across sites

  - SLA of ≥98% uptime

Current Bandwidth:

- Nyakabingo → 50 Mbps

- Rutongo → 50 Mbps

- Musha → 30 Mbps

3. Proposed Solution (To-Be)

3.1 Primary Connectivity – Starlink (Hyperlink Networks)

Based on the proforma:

| Site | Package | Expected Performance |
| --- | --- | --- |
| Nyakabingo | Business Ultra | 100–400 Mbps |
| Rutongo | Business Ultra | 100–400 Mbps |
| Musha | Business Plus | 70–400 Mbps |

Additional details:

- Contract duration: 24 months

- Latency: 25–60 ms

- Installation fee applicable

- Equipment remains provider property

3.2 Backup Connectivity – MTN Rwanda

Bandwidth downgrade:

| Site | Current | Proposed |
| --- | --- | --- |
| Nyakabingo | 50 Mbps | 30 Mbps |
| Rutongo | 50 Mbps | 30 Mbps |
| Musha | 30 Mbps | 20 Mbps |

MTN will continue to provide:

- VPN inter-site connectivity

- Failover support

- SLA-backed service

4. Scope of Work

4.1 Procurement Scope (Supply Chain)

- Procure Starlink services from Hyperlink Networks:

  - 2 × Business Ultra packages

  - 1 × Business Plus package

- Process installation fees

- Review and validate:

  - Contract duration (24 months)

  - SLA terms

  - Support model

- Initiate amendment with MTN:

  - Bandwidth downgrade per site

  - Contract adjustment / addendum

4.2 Technical Implementation (ICT)

A. Starlink Deployment

- Site survey & optimal dish positioning

- Installation of Starlink terminals

- Power and grounding setup

- Integration into existing network racks

B. Network Configuration

- Configure dual-WAN setup:

  - Primary: Starlink

  - Secondary: MTN

- Implement:

  - Automatic failover (WAN failover)

  - Load balancing (optional future phase)

  - Traffic prioritization (QoS)

C. VPN & Routing

- Maintain MTN VPN as:

  - Backup inter-site communication

- Evaluate:

  - Future migration of VPN to Starlink (optional phase)

4.3 Testing & Commissioning

- Validate:

  - Failover switching (Starlink → MTN)

  - MTN → Starlink restoration

- Performance testing:

  - Latency

  - Throughput

  - Stability

- User acceptance testing (UAT)

4.4 Documentation & Handover

- Updated network diagrams

- WAN configuration documentation

- Failover procedures

- Support escalation matrix

5. Deliverables

- Fully installed Starlink connectivity at all sites

- Configured failover between Starlink and MTN

- Optimized bandwidth usage

- Updated contracts (MTN & Hyperlink)

- Final implementation report

6. Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Starlink instability (weather) | MTN backup ensures continuity |
| MTN downgrade affecting VPN | Monitor and adjust QoS |
| Installation delays | Early coordination with vendor |
| Power issues | Ensure UPS support |

7. Timeline (Indicative)

| Phase | Duration |
| --- | --- |
| Procurement & Approval | 1–2 weeks |
| Installation | 1 week |
| Configuration | 3–5 days |
| Testing & Go-Live | 2–3 days |

8. Cost Consideration

From proforma:

- Business Ultra: 1,429,300 RWF / month (each)

- Business Plus: 663,900 RWF / month

- Installation: 69,000 RWF (one-time)

➡️ Total cost to be consolidated by Supply Chain

9. Success Criteria

- ≥99% internet availability (combined links)

- Seamless failover (no major downtime)

- Improved user experience (Sage, 4Flow, Office 365)

- Reduced dependency on single ISP