Progress Report No 9

| Project Name: Trinity Metals Mine Planning and Project support – Nyakabingo Mine |  |  |
| --- | --- | --- |
| Reporting Date: 31 March 2026 | Client Order Number: 0000003285 | Bara Contract Number: 2023-143 |
| Work Completed Since the Previous Progress Report: Work on ventilation planning, modelling and design: Ventilation design report and capital cost estimates Deswik Training |  |  |
| Work planned for the next period: Optimisation of ventilation plan Deswik training for mine planners Quarterly site visit |  |  |
| Deviations from the project programme or budget: Ventilation planning and designs is over budget. Additional, out of scope work that was completed includes: Site visit by ventilation engineer. Additional time of ventilation modelling and optimisation of ventilation plans. A variation order application has been submitted to Trinity Nyakabingo mine for the additional value. |  |  |
| Information/Action Outstanding: Approval of variation order by Trinity Completion of optimised ventilation plan by Bara |  |  |